| PURPOSE OF REPORT: | The report advises the Partnership Board of how NELCCG are performing against; six domains developed for the performance dashboard; three domains developed for quality dashboard and; six domains for risk. The dashboards are managed via the Delivery Assurance Committee, the Quality Committee and the Integrated Governance and Audit Committee. A summary of risks with a score of 16 or above is also included. For more detail on performance, risk and quality the latest integrated assurance report presented to the Delivery Assurance Committee and quality dashboard report presented to the Quality Committee can be found via the embedded files in the ‘Appendices / attachments’ section of this cover sheet. |
| --- | --- |
| Recommendations: | The Partnership Board is asked: to note judgements made against the domains of the dashboards to note the CCG Risk Management framework has been reviewed/refreshed and is shared with the committee on how we manage risks. Risk management is an increasingly important business driver and stakeholders have become much more concerned about risk. Risk may be a driver of strategic decisions, it may be a cause of uncertainty in the organisation or it may simply be embedded in the activities of the organisation. This framework aims to provide strategic direction, guidance and good management practice regarding embedding an integrated risk management approach, ensuring it is central to all CCG business, detailing clear lines of accountability and organisational responsibilities and arrangements. to note the Annual risk management reviews took place during June/July with the risk manager and risk assignee, with yet again a positive outcome. The purpose of these sessions are to provide the opportunity for Managers/Assignees to work together to review their risks paying particular attention to the risk ratings/internal controls and look at ways of improving our risk registers. This is also an opportunity to undertake an internal confirm & challenge and monitor static risks, for example if the risk rating of a risk hasn’t changed within the last 12 months, to evaluate whether the risk remains relevant and if so what actions will be taken. to note the information on future performance, quality and risk challenges to note information on Cancer 62 days waiting time to note update information on RTT for further feedback on ways to improve the report |
| Sub Committee Process and Assurance: | The Delivery Assurance Committee, the Quality Committee and the Integrated Governance and Audit Committee manage and assure the performance, quality and risks contained within these dashboards. |
| Implications: |  |
| Risk Assurance Framework Implications: | The dashboards and risks associated with them are managed via the Delivery Assurance Committee, the Quality Committee and the Integrated Governance and Audit Committee. |
| Legal Implications: | None |
| Equality Impact Assessment implications: | An Equality Impact Assessment is not required for this report. |
| Finance Implications: | There are a number of measures within the Performance Dashboard with a financial implication such as activity and Quality Premium measures, however the detail of these are dealt with separately within the Finance Report. |
| Quality Implications: | Quality implications are managed by the quality committee and escalated within the main body of this report. |
| Procurement Decisions/Implications (Care Contracting Committee): | None |
| Engagement Implications: | None |
| Conflicts of Interest | None |
| Strategic Objectives Short summary as to how the report links to the CCG’s strategic objectives | Sustainable Services The performance, quality and risk dashboards contain a number of national and local measures that support this objective. |
|  | Empowering People The performance, quality and risk dashboards contain a number of national and local measures that support this objective. |
|  | Supporting Communities The performance, quality and risk dashboards contain a number of national and local measures that support this objective. |
|  | Delivering a fit for purpose organisation The performance, quality and risk dashboards contain a number of national and local measures that support this objective. |
| NHS Constitution: | The Performance and Quality dashboards contain measures from the NHS Constitution and the performance and risks associated with these are managed and assured through the Delivery Assurance Committee, the Quality Committee and the Integrated Governance and Audit Committee. |
| Report exempt from Public Disclosure | No |

| Appendices / attachments |  |
| --- | --- |

Integrated Assurance & Quality Report

Introduction

The dashboards below represent an overview of performance and quality for health and social care services across North East Lincolnshire.

The performance dashboard consists of six domains and the quality dashboard three domains that incorporate all areas that North East Lincolnshire Clinical Commissioning Group strive to improve on. A judgement has been made of the status for each domain based on the measures and intelligence underpinning them. These judgements try to balance the current position with the expected outcome at the end of the year and weightings with respect to priority. They also represent the local perspective of performance and quality for North East Lincolnshire rather than the performance against the national definition which, on occasion, covers a broader footprint. It should be noted that those issues that have an impact on the CCGs corporate performance assessment will continue to be scrutinised at the Delivery Assurance Committee. The dashboards reflect performance for the six months of 2017-18. The Delivery Assurance Committee and Quality Committee, respectively, are asked to make a decision on the final status of the dashboards before reporting to the CCG Partnership Board.  Full exception report summaries are also included for Performance (appendix A) detailing performance of indicators that are underperforming, Provider-level Quality Dashboards (appendix B), risk (appendix C) detailing risks rated as 16 or higher.

Performance						  	          Quality

The risk heat maps are separated in to a CCG risk register and the CCGs Board Assurance Framework risks. These heat maps demonstrate the number of risks with a specific risk score. The risk summaries reflect the risk status as at 17th October 2017.

Risk Register risk profile					Board Assurance Framework risk profile

Performance Escalation

Cancer 62 day Waiting Times Performance

To update the Partnership Board on cancer 62 day waiting times performance.

Introduction

The national directive was for 70% of trusts to meet the national target of 85% by July 2017 and 100% to meet the target by September 2017.  Current national performance is 50% of trusts meeting the target (Humber, Coast and Vale (HCV) trusts do not meet these targets).

Performance

NELCCG performance for August 2017 was 56.41% against our submitted planned trajectory of 81.7% and current year to date performance on this measure is 72.68%.

Performance monitoring

- The HCV Cancer Alliance has commenced work with the Cancer Managers of each of our providers to secure development and oversee implementation of local recovery plans that will be monitored, the Northern Lincolnshire Planned Care Board receives monthly updates on performance against the recovery plan.

- Data is reviewed monthly, with detailed exception reporting for each breach.  In the main, these fall into the following categories;

- Patient Choice

- Capacity (workforce & radiology and diagnostics)

- Complex pathways

- Capacity of other treatment centres

- Significant increase in number of 2ww referrals

Current initiatives to aid recovery

- The CCG Cancer Clinical Lead, Service Lead and NLaG Cancer Manager are supporting NLaG to identify inappropriate 2ww referrals and raise with the individual GP/practice.

- NLAG are to undertake an audit of circa 1000 referrals sent via 2ww suspected pathway by GP/GDP/Opticians. This information should be available to the CCG by October/November.

- NLaG have employed dedicated cancer ‘turnaround’ manager to review all pathways/systems.

- Inter provider transfer policy agreed and in place.

- As part of the Right Care programme for gastroenterology, lower and upper GI pathways are being reviewed with hospital and primary care clinical staff working jointly to improve patient flow and appropriateness of interventions.

- Feedback from NLaG has included potential inappropriate use of the 2ww pathway for patients who may be urgent but not suspected cancer referrals. It is felt that this could be happening due to the long waits for patients not referred under the 2ww pathway. Therefore work is being undertaken to refine the ‘Urgent’ referral pathway to ensure that these patients are seen within an appropriate timescale and therefore this should help to prevent this from happening.

Additional Funding to aid recovery

To aid recovery of the 62 day target, NHSE made available additional funding.  NLaG successfully bid for the 1st and 2nd wave rounds and the following actions have commenced;

- Training commenced for 2 x additional Radiologists for MRI reporting of the Prostate Multi-Parametric MRI scans (expect this to take 6 months in total) but will have positive impact on the Prostate pathway.

- Colorectal Recovery Plans commenced end of August with additional evening clinics followed by Weekend Endoscopy lists – this will support the early part of the Colorectal pathway.

- Work underway to start local EBUS service – no start date yet.

- Work underway to appoint/back-fill for a CNS to support vetting of potential Straight To Test for MRI Prostate.

- Additional Cancer Tracker staff working to support tracking and to initiate moving “Live Somerset” MDT meetings in all tumour sites to help with streamlining pathways/workload so that more time can be spent on tracking patients at the beginning of their pathway to prevent any delays further down the pathway (this does currently happen but more resource was needed to support this).

CANCER ALLIANCE BID FOR TRANSFORMATION FUNDING

The HCV Cancer Alliance has recently received written feedback in relation to the Transformation Bids recently submitted. The Awareness and Early Diagnosis and Diagnostics Consolidation Elements of it were approved. The Living with and Beyond (LWAB) elements were delayed for approval until April 2018. This does not mean that we should not make any progress until next year in relation to the LWAB work stream and Treatment and Pathways work stream. The feedback received from the Regional Team is that they want us to concentrate our efforts during the next six months in meeting the 62 day waiting standard and the projects within the Awareness & Early Diagnosis and Diagnostics Consolidation work streams.

The individual schemes included within the Awareness & Early Diagnosis and Diagnostics Consolidation work streams are;

- Improving Lifestyle Choices and Raising Awareness (Cancer Champions)

- Primary Care Workforce Education and Training

- Screening and Active Case Finding

- Diagnosing Vague Symptoms

- FIT for Symptomatic Patients

- Diagnostic Capacity and Demand

- Networked Models of Radiology

- Developing the Diagnostic Workforce

The revenue funding approved is £0.6m in 2017/18 and £1.8m in 2018/19, and the capital is £2m in 2018/19 only.

Quality Escalation

The purpose of this report is to highlight the exceptions in Quality and to escalate items from the Quality Committee to the Board.

- Service Provider: Northern Lincolnshire and Goole NHS Trust

On enhanced quality surveillance due to finance, performance and quality.  The Trust remains in enhanced surveillance because sustained improvement in quality has not been achieved yet and there remains to be concerns about the quality of care delivered by the Trust.

The CQC inspected the Trust between October, November and December 2016 and submitted a Section 29A Warning Notice to the Trust in January 2017. The final outcome report was published 6th April 17 when the Trust achieved an overall rating of Inadequate.

The Trust was placed into financial and quality special measures in April 17, the Trust remain in these measures.

There remains to be concerns about the quality of service delivery, with particular regards to patient flow, nursing care, medical staffing, and organizational culture and waiting times.

The Trust has implemented an Improving Together Program to deliver the improvements required to address quality in the organization. The Program has now entered phase two.  The Trust has invested in an Executive Lead position to lead the Improving Together program.  Commissioners and Health Watch are working in partnership with the Trust to support the Improving Together Program Quality Assurance work stream.  With the Trust entering the second phase of the program Commissioners will be supporting further work streams, including the safer medication and discharge work streams.

Commissioners are working together to encourage and support quality improvement in the Trust.

- Service Provider: East Midlands Ambulance Service

There is noise in the local system concerning crew time response to 999 calls from medical centres.  The Trust is investigating four incidents reported to us in the past three months. Upon receipt of all four responses we plan to review the responses to determine if any further action needs to be taken.

- Service Provider: HMT St Hugh’s Hospital

The Trust continues to maintain a consistent level of incident reporting.  The Hospital are continuously developing and improving their Quality Report to provide a clear monthly summary in terms of performance and quality.

- Service Provider: Thames Transport Service

There has been negative media attention concerning TASL this September.  There is a risk that negative media attention may continue which will impact public perceptions of the service, staff morale, and increased stakeholder scrutiny and provider relationships.   It is recognized that clear and consistent communication with stakeholders, the public and the provider is required to reduce the risk of ambiguity and manage the risks.

NELCCG commissioners continue to work with the service provider to help to identify areas for quality improvement by conducting unannounced site visits, to date two visits have been conducted which identified areas for improvement.

TASL has been subject to an unannounced CQC inspection on the 19th of September 2017.  TASL CEO has shared a briefing paper following the inspection with Commissioners, we await the CQC findings.

- Development of a Northern Lincolnshire Infection Prevention and Control Network Meeting

NELCCG Quality Team has collaborated with the local Trust and stakeholders to form a Northern Lincolnshire Infection Prevention and Control network meeting.  Forming a local network to share best practice, complete reflections with peers, drive improvement across the local health and social care economy and provide a support mechanism for IPC Leads.

Items for Escalation from the Quality Committee

Members of the NELCCG Quality Committee, which took place on 12/10/2017, identified three items for escalation to the Board, these items are summarised below:

•	Mental Capacity Act (2015) - Training Review, Analysis and Recommendations.

The Committee received an excellent overview of the work completed by Emma Overton to review the training accessed locally for MCA.  The review identified 16 pertinent recommendations; the key theme identified was that the access to quality training locally needs to be improved.  The Quality Committee recognised the significance of the findings and the extensive piece of work completed by Emma.  The Committee have arranged to receive an update on progress with the recommendations in three months.

•	Position of NLaG – Quality Risk Profile.

The Quality Risk Profile for NLaG was refreshed and the Committee was briefed on the current position.

•	Deep dives in Pressure Ulcers, Discharge and Medication.

The Committee acknowledged the work to date and recognised that further work with the Service Provider is required.

Appendix A - Performance Exception Summary

| Code | Indicator | Quality Measure? | Latest period | Year to date | Year End Forecast |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Period | Target | Value | Status | Target | Value | Status |  |
| Positive experience |
| DAC1000 | Total time in A&E: four hours or less | Yes | September 2017 | 87.29% | 87.41% |  | 83.47% | 84.51% |  |  |
| DAC1020 | Cancelled Operations offered binding date within 28 days | Yes | Q1 2017/18 | 0.96% | 5.34% |  | 0.96% | 5.34% |  |  |
| DAC1040 | Numbers of unjustified mixed sex accommodation breaches | Yes | August 2017 | 0 | 38 |  | 0 | 89 |  |  |
| DAC1065 | Friends & Family - Ambulance - % Who would recommend 'SAT' service | Yes | July 2017 | 94.33% | 100% |  | 95.61% | 95.24% |  |  |
| DAC1070 | Friends & Family - Ambulance Response (PTS) | Yes | July 2017 | 0.64% | 0.57% |  | 0.66% | 0.57% |  |  |
| DAC1075 | Friends & Family - Ambulance Response (SAT) | Yes | July 2017 | 0.12% | 0.04% |  | 0.12% | 0.07% |  |  |
| DAC1080 | Friends & Family - AAE % Who would recommend service | Yes | July 2017 | 85.86% | 75.56% |  | 86.92% | 76.86% |  |  |
| DAC1090 | Friends & Family - AAE Response (NLAG) | Yes | July 2017 | 12.78% | 7.64% |  | 12.69% | 6.74% |  |  |
| DAC1110 | Friends & Family - Inpatient Response (NLAG) | Yes | July 2017 | 26.17% | 14.28% |  | 26.1% | 14.38% |  |  |  |  |
| DAC1120 | Friends & Family - Outpatient - % Who would recommend service | Yes | July 2017 | 93.69% | 76% |  | 93.7% | 81.89% |  |  |  |  |
| DAC1130 | Friends & Family - Outpatient Response | Yes | July 2017 | 6.44% | 0.23% |  | 6.37% | 0.21% |  |  |  |  |
| DAC1150 | Friends & Family - Community Response (CPG) | Yes | July 2017 | 3.74% | 0.85% |  | 3.57% | 1.08% |  |  |  |  |
| DAC1180 | Friends & Family - Maternity - Combined % Who would recommend | Yes | July 2017 | 95.86% | 92.23% |  | 96.09% | 94.47% |  |  |
| DAC1190 | Friends & Family - Maternity Response (NLAG) Birth | Yes | July 2017 | 23.64% | 17.48% |  | 23.87% | 13.2% |  |  |
| DAC1210 | Proportion of GP referrals made by e-referrals | Yes | July 2017 | 60% | 31.38% |  | 60% | 31.38% |  |  |
| DAC1220 | Overall Experience of Making a GP Appointment | Yes | 2016/17 | 73.26% | 71.53% |  | No data available for 2017/18 |  |
| Preventing avoidable harm |
| No exceptions |
| Delaying and reducing the need for care and support |  |  |  |  |  |  |  |  |  |  |
| DAC3070 | Delayed transfers of care (delayed days) from hospital per 100,000 population (aged 18+). | Yes | August 2017 | 222.43 | 161.75 |  | 1121.75 | 1265.34 |  |  |
| DAC3080 | Delayed transfers of care (delayed days) from hospital per 100,000 population (aged 18+) which are an NHS responsibility | Yes | August 2017 | 92.43 | 149.8 |  | 911.56 | 1082.87 |  |  |
| DAC3130 | The proportion of older people aged 65 and over offered reablement services following discharge from hospital. | No | March 2016 | 1.35% | 1.30% |  | No data available for 2017-18 |  |
| DAC3175 | Total Elective Spells (Specific Acute) | No | July 2017 | 2363 | 2394 |  | 9226 | 10008 |  |  |
| DAC3215 | Consultant Led First Outpatient Attendances (Specific Acute) | No | July 2017 | 3544 | 4245 |  | 13838 | 16354 |  |  |
| DAC3235 | Consultant Led Follow-Up Outpatient Attendances (Specific Acute) | No | July 2017 | 7000 | 7964 |  | 27332 | 29623 |  |  |
| DAC3270 | Total Referrals made for a First Outpatient Appointment (G&A) | No | August 2017 | 4402 | 4192 |  | 20808 | 21060 |  |  |
| DAC3276 | Total Other Referrals made for a First Outpatient Appointment (G&A) | No | August 2017 | 1723 | 2022 |  | 8144 | 10346 |  |  |
| Enhancing quality of life |
| DAC4090 | % people who have depression and/or anxiety disorders who receive psychological therapies | No | June 2017 | 1.4% | 1.46% |  | 4.2% | 3.99% |  |  |
| Preventing people from dying prematurely |
| DAC5001 | ARP Category 1 Mean Response Time – Calls from people with life-threatening illnesses or injuries | Yes | August 2017 | 00:07:00 | 00:08:01 |  | 00:07:00 | 00:08:01 |  |  |
| DAC5011 | ARP Category 2 Mean Response Time – Emergency calls | Yes | August 2017 | 00:18:00 | 00:23:47 |  | 00:07:00 | 00:23:47 |  |  |
| DAC5013 | ARP Category 2 90th centile response time – Emergency Calls | Yes | August 2017 | 00:40:00 | 00:50:44 |  | 00:15:00 | 00:50:44 |  |  |
| DAC5023 | ARP Category 3 90th centile response time – Urgent Calls | Yes | August 2017 | 02:00:00 | 02:25:07 |  | 02:00:00 | 02:25:07 |  |  |
| DAC5040 | Ambulance 30 minute average turnaround time target - DPOW | No | August 2017 | 30 mins | 37.26 mins |  | 30 mins | 39.83 mins |  |  |
| DAC5110 | Cancer 62 Days Referral to Treatment (GP Referral) | Yes | August 2017 | 81.7% | 56.41% |  | 80% | 72.68% |  |  |
| DAC5120 | Cancer 62 Days Referral to Treatment (Screening Referral) | Yes | August 2017 | 90% | 83.3% |  | 90% | 76.6% |  |  |
| DAC5130 | Cancer 62 Days Referral to Treatment (Consultant Upgrade) | Yes | August 2017 | 90% | 100% |  | 90% | 50% |  |  |
| DAC5150 | Summary Hospital Mortality Index (SHMI) - NLAG | Yes | March 2017 | 100 | 113.68 |  | No data available in 2017/18 |  |
| Helping people recover from ill health or injury |
| DAC6040 | RTT - Number of completed admitted RTT pathways | Yes | August 2017 | 860 | 995 |  | 4063 | 4810 |  |  |
| DAC6045 | RTT - Number of completed non-admitted RTT pathways | Yes | August 2017 | 2652 | 2725 |  | 12535 | 13419 |  |  |
| DAC6050 | RTT - Number of new RTT pathways (clock starts) | Yes | August 2017 | 4402 | 4816 |  | 20809 | 22271 |  |  |
| DAC6060 | RTT - Incomplete Patients: % Seen Within 18 Weeks | Yes | August 2017 | 80% | 75.54% |  | 80% | 76.27% |  |  |
| DAC6070 | RTT – No. waiting on incomplete pathway 52+ wks | Yes | August 2017 | 0 | 36 |  | 0 | 212 |  |  |

Appendix B – Provider-level Quality Surveillance Ratings

Appendix C – Risk Exception Summary

Section 1 – Board Assurance Framework

The table below reflects risks rated as 15+ (high to significant) on the assurance framework as at 17th October 2017

Component 2: Better Care - How is the CCG faring with its care redesign, performance of constitutional standards, and its outcomes, including in important clinical areas?

| Risk Code | Risk Summary | Risk Assignee | Initial Risk Rating | Current Risk rating | Current Risk Trend Icon | Last reviewed date | Control | Notes & History Latest Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-BAF.2002 | Risks in delivery of key annual performance indicators and standards including constitutional standards | Martin Rabbetts | 12 | 20 |  | 13 Oct 2017 | Assurance on controls | Regular reporting in to Partnership Board, Delivery Assurance Committee, CoM and the operational leadership team. | 12/10/18 Martin Rabbets advised there were no changes to note but that there will be a full update provided in November. |
|  |  |  |  |  |  |  | Positive Assurances | July 2017 NHS E have acknowledged the CCG is taking an active leadership role to address the issues in relation to NLaG. Further assessment of six clinical areas in the CCG Improvement and Assessment Framework demonstrate that NEL are in the top five CCGs in the country, although improvement is required in three. NHSE's overall assessment of the CCG in the improvement and assessment framework was ‘Good’. 2016/17 Year end position of ASC targets was positive and the Local Account was positive. |  |
|  |  |  |  |  |  |  | Gaps in controls | None |  |
|  |  |  |  |  |  |  | Gaps in assurances | We recognise that there is significantly increased oversight and assurance mechanisms in place to oversee NLaG performance however gaps will remain until we start to see improvements feeding through. |  |

| Risk Code | Risk Summary | Risk Assignee | Initial Risk Rating | Current Risk rating | Current Risk Trend Icon | Last reviewed date | Control | Notes & History Latest Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-BAF.2003 | NLaG Service Sustainability | Helen Kenyon | 20 | 20 |  | 16 Aug 2017 | Assurance on controls | Chief Executive representation from NL & NEL CCGs and NLaG on the system transformation group CCG representation on all 4 sub groups of the system transformation group The CCG's Acting Chief Financial Officer represents the CCG on the aligned incentive contract group | 15/08/17 Helen Kenyon advised that the aligned incentive contract has been agreed between NL and NEL CCGs and NLaG to reduce the financial risk to NLaG. New leadership arrangements have been adopted which replace the previous contract management arrangements and the Chief Executives from the 3 organisations are members. The leadership group is called the System Transformation Group and there are 4 sub-groups beneath it (A&E Delivery Board, Planned Care-RTT, Finance and Resources, Quality) which are focusing on the key areas for change within the Trust. There is a System Improvement Board which is chaired by NHS Improvement with the two CCGs and NHS England present to oversee progress on areas identified for improvement from the CQC report and financial special measures. |
|  |  |  |  |  |  |  | Positive Assurances | System Improvement Board whose membership includes NHS England and NHS Improvement. NEL CCG received positive feedback in the second quarter of 2017 at its assurance meeting with NHS England The STP In-hospital Working Group is starting to work more effectively and is addressing issues across providers The ACP is getting more involved and starting to come up with proposals to divert activity and release pressures |  |
|  |  |  |  |  |  |  | Gaps in controls | All of the controls listed have only been established very recently and need time to bed in before their full effectiveness can be evaluated |  |
|  |  |  |  |  |  |  | Gaps in assurances | All of the assurances listed have only been established very recently and need time to bed in before their full effectiveness can be evaluated Lack of consistent leadership presence from NLaG due to a number of time limited interims in place |  |

Component 3: Sustainability-How is the CCG remaining in financial balance & securing good value for patients and the public from the money it spends?

| Risk Code | Risk Summary | Risk Assignee | Initial Risk Rating | Current Risk rating | Current Risk Trend Icon | Last reviewed date | Control | Notes & History Latest Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-BAF.3005 | Instability in partnership finances or services/costs leads to unaffordable consequences for members of the health care system within the current year | Laura Whitton | 12 | 20 |  | 06 Oct 2017 | Assurance on controls | Routine financial reports to partnership board Delivery Assurance Committee scrutiny of financial plan delivery QiPP monitoring Local health community financial monitoring and reporting via the SIB Finance group, ACP finance group | 4/10/17 Laura Whitton reviewed the risk and advised there is no change to the position reported in September. 12/09/17 Laura Whitton advised the level of risk has been increased (likelihood now rated at 5), reflecting (i) where NLG are with regard to finalising their Finance Recovery Plan and (ii) NLGs finance position year to date, which is behind target. |
|  |  |  |  |  |  |  | Positive Assurances | SIB (System Improvement Board) assurance process Medium Term Financial Plan reports to IG&A and board Internal audit plan is risk -based |  |
|  |  |  |  |  |  |  | Gaps in controls | None identified |  |
|  |  |  |  |  |  |  | Gaps in assurances | None identified |  |

Component 4: Leadership - How good is the quality of the CCG's leadership and the quality of it's plans? How does the CCG work with its partners and the governance arrangements that the CCG has in place to ensure it acts with probity, for example, in managing conflicts of interest?

| Risk Code | Risk Summary | Risk Assignee | Initial Risk Rating | Current Risk rating | Current Risk Trend Icon | Last reviewed date | Control | Notes & History Latest Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-BAF.4001 | Failure to consult on significant service change/redesign which could lead to a breach of statutory duty | Lisa Hilder | 3 | 16 |  | 06 Oct 2017 | Assurance on controls | Monitoring of outputs by the Health Overview and Scrutiny Committee | 5/10/17 Lisa Hilder reviewed this risk and advised that the NL/NEL team is currently not adequately resourced and this has been flagged within the governance framework of the System Transformation programme. Limited or no progress can be made until capacity is increased. In view of this Internal control 4001g (Comms and Engagement Group) has been amended from fully effective to partially effective and the risk rating has been raised to 4x4. |
|  |  |  |  |  |  |  | Positive Assurances | NHS England annual report has been rating the CCG as positive for comms and engagement. |  |
|  |  |  |  |  |  |  | Gaps in controls | Some limited staff member gaps in understanding organisational processes around consultation for significant service change/redesign |  |
|  |  |  |  |  |  |  | Gaps in assurances | N/A |  |

Section 2 - Risk Register

The table below reflects risks rated as 15+ (high to significant) on the risk register as at 17th October 2017

Guidance Component 2: Better Care - How is the CCG faring with its care redesign, performance of constitutional standards, and its outcomes, including in important clinical areas?

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-RR.2005 | RTT Performance | Pauline Bamgbala | 20 | 25 |  | 10 Oct 2017 | CCG-RR.2005a Performance Reporting | Robust performance reporting is produced for the Service Lead to act upon and is monitored at Delivery Assurance Committee with escalation to CoM and Partnership Board. | 6/10/17 Pauline Bamgbala reviewed this risk and updated as follows: RTT: Performance continues to deteriorate and this is being monitored via the Planned Care Board. There are a number of initiatives in place to address performance issues: Streaming of Referrals: NLaG progressing pilot work programme which has a focus on the streaming of referrals, so that any waiting lists can be prioritised on patient quality and safety grounds Referral Criteria and Commissioning thresholds: Development of a single set of referral criteria and commissioning thresholds that is consistent across all three CCGs working with NLaG, extending to the other CCGs in Midlands and East if possible Establish a shared referral management system: With the capability to identify and utilise capacity outside of NLaG, for services where there are considerable capacity challenges and resulting backlogs Outsourcing: CCGs contacting neighbouring acute trusts to determine capacity elsewhere Demand Management : CCGs and NLaG working jointly on: - development of a local clinical peer review scheme - retrospective peer review - identification of where highest levels of consultant to consultant referrals are and what action is required to reduce where appropriate |
|  |  |  |  |  |  |  | CCG-RR.2005c System wide transformation group establised | RTT has been established which will feed into the System Transformation Board and the System Improvement Board. Senior leadership at those meetings with clinically led planning to redesign services for optimum efficiency and effectiveness. Clinical engagement has been secured from both the Trust and the CCG. Structured programme approach to be taken using Right Care principles. Initial priority areas identified are respiratory, cardiac and gastro. |  |
|  |  |  |  |  |  |  | CCG-RR.2005e Clinical Harm Review Groups | There are two clinical harm review groups (one at NLaG and one external). They both meet on a monthly basis and Jan Haxby is a member of both groups. |  |

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| CCG-RR.2004 | Failure to achieve Accident and Emergency 4 hour targets | Andy Ombler | 16 | 20 |  | 12 Oct 2017 | CCG-RR.2004b Action Plans | Action plans focussing on all issues with potential impact on 4 hour A&E wait performance. The action plan has been revised to take into account the ECIP findings and recommendations. | 12/10/17 Andy Ombler advised September performance had dipped very slightly to 84% at DPoW but has risen in the first 10 days of October to 88.5%. Under the NHS monitoring of the Northern Lincolnshire Winter Plan the overall trust position must be 90% for Q3 and Q4 and for October (Month 1 of Q3 up to 10th October ) the Trust performance stands at 90.5%. Work continues on the winter plan priorities to support this performance under the oversight of the A&E Delivery Board. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | CCG-RR.2004c A&E Delivery Board | A&E delivery board established as part of a national requirement to ensure system wide ownership and delivery against the A&E target required. |  |

| CCG-RR.2003 | On-going failure to meet Clinical Handover time targets for EMAS patient delivery at DPoW A&E | Andy Ombler | 8 | 15 |  | 12 Oct 2017 | CCG-RR.2003a CCG | Performance is monitored by the CCG and reported to the A&E Delivery Board. Monitoring only. | 12/10/17 Andy Ombler advised the August position on pre-clinical handover improved again by a further ~3 minutes from June by ~2.5 minutes, with a slight deterioration in the post clinical time taking the total to ~3.7mins which is the best performance in the 12 months. Andy attended a meeting between EMAS and NLaG to review handover protocols – in particular the introduction of the electronic patient transfer notes which should improve handover performance. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Guidance Component 3: Sustainability - How is the CCG remaining in financial balance and securing good value for patients and the public from the money it spends?

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-RR.3003 | Adult ADHD Pathway breakdown | Leigh Holton | 20 | 16 |  | 06 Oct 2017 | CCG-RR.3003a Council of Members (CoM) | Quarterly report to CoM | 04/10/17 Update from Leigh Holton – Work continues with providers Navigo & Care Plus Group to develop a specialised pathway in partnership. Potential funding is still to be clarified. Exploration of options on wider footprint is continuing with Hull and East Riding. Current progress still falls short of implemented changes to the system so we are unable to lower the risk rating at this time. |
|  |  |  |  |  |  |  | CCG-RR.3003b PALs monitoring logs | Monitoring through logs of concerns via PALs |  |

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-RR.3015 | Supported Living and Extra Care Housing - Housing Benefit Review | Sarah Moody | 16 | 16 |  | 14 Sep 2017 | CCG-RR.3015a Joint Housing Strategy Meeting | Representatives from NELC and the CCG are members of this meeting | 13/9/17 Sarah Moody advised that controls are now in place and a joint delivery plan in plan has been put in place by the CCG and Council to resolve the issue in the next few months. One control has been amended and 3 more added. |
|  |  |  |  |  |  |  | CCG-RR.3015c Refresh of extra care housing strategy | The CCG is currently undertaking a refresh with an updated evidence base. Agree a joint ECH strategy between the CCG and NELC |  |
|  |  |  |  |  |  |  | CCG-RR.3015d Transitional planning for CCG/NELC Union | Extra care housing delivery will be a strategic priority for the CCG/NELC union. |  |
|  |  |  |  |  |  |  | CCG-RR.3015e Commitment from HCA to ensure the scheme is affordable by the allocation of a funding grant | The regional team HCA are very supportive and are under spent in North East Lincolnshire so this is a priority for them |  |
|  |  |  |  |  |  |  | CCG-RR.3015f Exploring options for housing providers | Looking into a mixed tenure approach/exploring options for housing providers to deliver flexible schemes and other types of units and general housing need if required. |  |
|  |  |  |  |  |  |  | CCG-RR.3015g Determining rent levels | Ensuring the rent level is determined at affordable levels through a combination of funding/design spec. |  |
|  |  |  |  |  |  |  | CCG-RR.3015h Review and realignment of Council policy | Ensuring that there is a review and realignment of council policy in respect of housing allowance allocations for supported housing. |  |

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-RR.3016 | Mental Health SilverLink Computer System (Non-Disclosure Applies) | John Mitchell | 15 | 15 |  | 13 Oct 2017 | CCG-RR.3016a NAViGO Project Team. Project Plan in place which is overseen by the Programme Manager | A NAViGO project team with a CCG representative (Associate Director IT) is to be established | 12/10/17 John Mitchell advised that conversations with NHSE continue with a focus on using excess in the STP BAU fund to support the migration. A meeting with TPP (potential\probable) supplier took place on 11/10/17 to specifically look at issues around reporting and of greater concern a data extract facility used to feed clinical dashboards. TPP will provide further response to the queries. |
|  |  |  |  |  |  |  | CCG-RR.3016b Veeam back up of data | Veeam backup of data and servers at 3am every day |  |
|  |  |  |  |  |  |  | CCG-RR.3016c Real time replication | The SilverLink databases are replicated in real time from Care Plus Group primary datacentre to Care Plus Group secondary datacentre. |  |
|  |  |  |  |  |  |  | CCG-RR.3016d Programme Manager | Programme Manager now in place. This is funded by CCG, his role is to manage the project and the implementation of procurement. |  |

Guidance Component 4: Leadership - How good is the quality of the CCG's leadership and the quality of it's plans? How does the CCG work with its partners and the governance arrangements that the CCG has in place to ensure it acts with probity, for example, in managing conflicts of interest?

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-RR.4007 | eMBED IT Core Contract Delivery | John Mitchell | 25 | 20 |  | 13 Oct 2017 | CCG-RR.4007a Contract in place | Contract, detailing service spec and SLA in place. Currently meeting contractual IT KPIs. | 12/10/17 John Mitchell advised that an extra meeting was held on 09/10/17 with eMBED where they agreed that their project service wasn’t delivering in appropriate timescales. Some staff changes have been made and if these changes prove to be successful then the risk score may decrease. Evidence is required first though. |
|  |  |  |  |  |  |  | CCG-RR.4007b Contract Management Arrangements in place | Regular monthly contract monitoring meeting in place with the CCG and eMBED. Attendees are John Mitchell and Eddie McCabe and Julie Wilson attends as required |  |
|  |  |  |  |  |  |  | CCG-RR.4007c Programme and Project Plans | Programme controls in place, used to manage the Project and Programmes. eMBED able to provide tracking tool. The CCG has taken steps to monitor programme delivery on a monthly basis via the Strategy Board. |  |
|  |  |  |  |  |  |  | CCG-RR.4007d Risk Management in Place | Part of programme management of controls and is also picked up by the Strategy group. |  |
|  |  |  |  |  |  |  | CCG-RR.4007e Local Primary Care Strategy Group | A locally focused strategic group has been formed to provide a gateway for approving use of project days and monitoring progress on delivery. This control is scored at partially effective as the group is currently in its initiation phase. |  |

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-RR.4017 | Establishment of the Accountable Care Partnership in North East Lincolnshire | Helen Kenyon | 25 | 20 |  | 18 Aug 2017 | CCG-RR.4017a ACP Shadow Board | The CCG is a member of the board. Regular meetings take place to discuss the development of the ACP | 17/8/17 Helen Kenyon advised the ACP has identified 3 service priorities for action and has recently added a 4th, and to ensure progress is made against each of the areas increased reporting arrangements were agreed at the last ACP meeting. It was also agreed that the commissioner (CCG & Council ) will produce a more formal statement of what we expect the ACP to be able to demonstrate as part of its assurance of sufficient progress. A meeting has been established to pull together the high level progress requirements & timeline for the commissioner to send to the ACP. |
|  |  |  |  |  |  |  | CCG-RR.4017b ACP Workplan in place | Work plan in place to provide timelines and oversight on progress of the ACP |  |
|  |  |  |  |  |  |  | CCG-RR.4017c Programme Manager appointed | A Programme Manager has been appointed to support overall delivery of the programme |  |

| Risk Code | Risk Summary | Risk Assignee | Original Risk Rating | Current Risk Rating | Current Risk Trend | Last Reviewed Date | Internal Controls | Description of Control | Latest Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CCG-RR.4004 | The DoLS system is unable to cope with the increasing number of requests for authorisation | Bruce Bradshaw | 16 | 16 |  | 13 Oct 2017 | CCG-RR.4004a Monitoring of activity at DAC and Safeguarding Board | The risks are monitored as part of the strategic plan and reviewed on a regular basis by the Chair (Jan Haxby NELCCG) and via the Safeguarding Adults Operational Leadership Group. | 12/10/17 Bruce Bradshaw advised there are no changes to this risk and the update remains as provided in August. 24/8/17 A full risk management review was carried out with Helen Kenyon and Bruce Bradshaw. The risk description was updated and new controls added. Due to the controls in place the risk rating was reduced. Increased controls are in place however we have still to take individuals through the full process to test out effectiveness of the system. This will be monitored over the coming months and if a positive assurance is received via the courts this will provide assurance that systems and processes are working reducing the likelihood of this risk materialising. |
|  |  |  |  |  |  |  | CCG-RR.4004b Strategic Mental Capacity Group | The Group monitors strategic change and works jointly with the CCG and providers. Group membership is led by CCG representation with other members coming from key stakeholders and voluntary sector. Reports from this group go to the CCG Quality Committee and Operational Leadership Group. |  |
|  |  |  |  |  |  |  | CCG-RR.4004c Additional capacity to support delivery | Increasing recruiting and training best interest assessors across the local health and social care economy. Increase in staffing to support operational delivery and advice. |  |
|  |  |  |  |  |  |  | CCG-RR.4004d Joint working with NELC legal team | Help and support to develop and deliver a process for applications to the court of protection for deprivations in non-standard settings. Providing front end legal advice to practitioners. |  |

# Text boxes

Agenda Item 09

Report to (Board/Sub-Committee): NEL CCG Partnership Board

Date of Meeting: 9th November 2017

Subject: Integrated Assurance and Quality Report

Presented by: Eddie McCabe Assistant Director – Contracting & Performance, Jan Haxby Director of Quality & Nursing

STATUS OF THE REPORT

For Information

For Discussion				(

For Approval / Ratification