North East Lincolnshire CCG

| Report to: | NEL CCG Partnership Board |
| --- | --- |
| Presented by: | Zena Robertson/Peter Melton |
| Date of Meeting: | 10th January 2012 |
| Subject: | Mortality Action Plan and Verbal Update |
| Status: | OPEN CLOSED |
| Agenda Section: | STRATEGY COMMISSIONING OPERATIONAL ISSUES |

| OBJECT OF REPORT |  |
| --- | --- |
| To Provide the Governing Body with an update on the actions taken following the external review of mortality in Northern Lincolnshire. |

| STRATEGY |  |
| --- | --- |
| Links to delivering sustainable quality services. |

| IMPLICATIONS |  |
| --- | --- |
| To provide the Governing Body with assurance of improvement in outcomes for patients |

| RECOMMENDATIONS (R) AND ACTIONS (A) FOR AGREEMENT |
| --- |
| Governing Body to note the verbal update and the attached action plan |  | Agreed? |

|  |  | Yes/No | Comments |
| --- | --- | --- | --- |
|  | Does the document take account of and meet the requirements of the following: |  |  |
| i) | Mental Capacity Act | yes | Actions taken as part of the plan where relative will take account of the MCA |
| ii) | CCG Equality Impact Assessment | yes | EI will be taken into account in any service change and a EI assessment undertaken if appropriate. |
| iii) | Human Rights Act 1998 | N/A |  |
| iv) | Health and Safety at Work Act 1974 | N/A |  |
| v) | Freedom of Information Act 2000 / Data Protection Act 1998 | yes |  |
| iv) | Does the report have regard of the principles and values of the NHS Constitution? www.dh.gov.uk/en/Publicationsandstatistics/Publications/PublicationsPolicyAndGuidance/DH_113613 | yes |  |

| Report Action | Detailed action | Lead | Timescale | Progress update | RAG | Sustainable services impact |
| --- | --- | --- | --- | --- | --- | --- |
|  | OUTCOME 1 IMPROVING PATIENT EXPERIENCE |
| Joint work with commissioners and providers on unplanned care, LTC, Dementia etc. on patient experience. Co-production of patient pathways through appropriate engagement methods for each CCG. | NL-complete the work using experience led commissioning on EOL & LTC and agree forward programme across additional pathways for 13/14 | Caroline Briggs | 31.03.13 | Model of Care agreed by NL CCG, for discussion 13.12.12 workshop re sustainable services | A | Ensure improved patient experience is a key outcome of all SSP themes. |
|  | NEL – each triangle to define and agree priorities for 13/14 | Peter Melton | 13.12.12 |  | A |  |
|  | Triangles to meet with Peter Melton to agree priorities for the primary care quality strategy | Peter Melton | NEL CoM to consider draft priorities 5.12.12 |  | A |  |
| Embed the family and friends test in the hospital CQUINs scheme | F & F test in hosp CQUINs Agree draft CQUINs Contract discussions Agreed & in contracts | Zena R & Karen Rhodes HK/CB HK/CB | Ensure measures are in 2013/14 contracts Dec 2012 Jan 2013 Feb 2013 | Discussion initiated with CSU to ensure FFT CQUIN in contracts for 13/14 | A A A A |  |
| Develop appropriate measures established for other providers | Develop other measures for H&EY | Jane Ellerton | January 2013 |  | A |  |
|  | NEL – develop measurable outcomes in the triangle objectives on patient experience | Helen Kenyon | NEL – in triangle objectives for 13/14 by May 2013 |  | A |  |
|  | Goole - | Hilary Gledhill |  |  | G |  |
|  | OUTCOME 2 EVIDENCE BASED PRACTICE |
| Evidence regarding best practice continually evolves and emerges, often nationally such as through publications from organisation such as the National Institute for Health and Clinical Excellence (NICE). Clinical practice within the Trust therefore needs to change and evolve to adopt best practice and this requires individual and groups of clinicians – clinical champions - to identify, adopt and disseminate best practice. These individuals would form part of the Quality Network. | Board support for development of Quality Network | Board | August 12 | Completed | G |  |
|  | Develop Quality Network | J Daws, C Hunt, S Mainprize | October 12 & ongoing | Work ongoing | G |  |
|  | OUTCOME 3 RIGHT STAFFING LEVELS |
| Having the right staffing levels is not just about numbers, it is also about the skills and skill mix of the clinical teams, the leadership skills of the team leaders, the case mix of patients they are responsible for and the robustness of staffing arrangements. It is also important that levels are right seven days a week if the excess mortality seen at weekends is to be reduced. | Determine the correct staffing levels, particularly at weekends using external validation tools where available such as Safer Nursing Care Tool (SNCT), Birthrate Plus | K Dunderdale E Scott | Ongoing | First assessments completed. SNCT results will be available January 2013 for Medicine Group | A |  |
|  | Implement e-rostering governance tool to enable real time monitoring of staffing levels | K Dunderdale | November 2012 | HealthAssure commissioned to develop. Demonstration given to QPEC of a draft version | A |  |
|  | Implement 7 day working | P Wisher | Tbc after consultation | Work commenced | A |  |
|  | Provide regular report to the Board on actual staffing levels | K Dunderdale | Presented Nov 12 and ongoing. | Reports presented each month | G |  |
|  | OUTCOME 4 DETERIORATING PATIENT |
| Review existing CQUIN scheme for deteriorating patients and seek agreement by all parties to amend in year to addresses key issues | Proposed revision - roll into next rear 2013/14 CQUIN scheme | Helen Kenyon | Update to mortality action group by November 19 on agreement reached | NL & NEL agree process with CSU to develop 13/14 CQUINS | A |  |
|  | Develop and agree an appropriate scheme for 13/14 Agree draft CQUINs Contract discussions Agreed & in contracts | Zena Robertson/Karen Rhodes for 13/14 scheme | 28.02.13 Dec 2012 Jan 2013 Feb 2013 | NEL & NL discussion via contract lead Further discussion in development of CQUINs for 13/14 Lynn Poucher (CSU) to arrange a meeting for N , NEL and ERY re in year development of framework ready to start new CQUIN 1/4/13 | A A A A |  |
|  | OUTCOME 5 BETTER CARE OF THE DETERIORATING PATIENT |
| The analysis of the data undertaken by THL in relation to patient risk categories and to weekend mortality, the observations and advice of the THL team and the experience from elsewhere all point to the need to improve the care of the deteriorating patient. There are two principle strands to this work. First, patient observations need to be made in a timely fashion that reflects the clinical needs of the patient, these observations need to be recorded in a clear format, and they need to be assessed in a systematic manner. Secondly, cardiac arrests need to be reduced as they can represent the ultimate failure to react to a deteriorating patient. | Deteriorating Patient Group (DPG) to be established to oversee all work in this area | K Dunderdale | August 12 | Completed | G |  |
|  | Bedside documentation to be reviewed and revised | K Dunderdale /DPG | October 12, & ongoing | Commenced. Nursing Documentation Steering Group set up and working with clinical portal WebV team. Nursing admission and patient at risk tools updated | G |  |
|  | National Early Warning System to be introduced | K Dunderdale /DPG | November 12 | Implemented and to be audited March 2013 | G |  |
|  | Audit of cardiac arrests to be undertaken, encompassing care up to 48 hours prior to arrest | S Heath/ M Hockey | October 12 | Audit underway and first cases reviewed | G |  |
|  | Preventable factors identified and actions to reduce agreed | S Heath/ M Hockey /DPG | December 12 | To start once audit results available | A |  |
|  | Target for reduction of cardiac arrests to be agreed with the Board | E Scott | December 12 | Audit results required | R |  |
|  | Establish the use of SBAR as the communications gold standard throughout the Trust | S Mainprize | March 13 | Underway in some clinical areas. SBAR awareness sessions undertaken, more planned. Pathologists ensuring junior medical staff use SBAR. Nursing handover tool in draft form which uses SBAR. | A |  |
|  | OUTCOME 6 REDUCING HARM |
| Developing a patient safety culture across the system | Primary care – roll out incident reporting in primary care. Work jointly with providers to share learning across the system. | Paul Twomey Karen Rhodes Zena Robertson Hilary Gledhill | 31.01.13 | NL developed written guidance on incident reporting, approved by the CCG Quality group and discussions with LAT awaited before circulation and implementation. Systems already in place for NEL. | A A |  |
|  | Review guidance on reporting & agree with LAT NL CCG finalise intranet site re concerns and issues LAT to advise on method for shared learning across patch | Karen Rhodes and Zena Robertson James Tindall Paul Twomey | 30.1.13 31.12.12 30.1.13 |  | A A A |  |
|  | Commissioners to work with LAT to understand the model of delivering primary care quality for the future & identify system for sharing learning | Peter Melton Margaret Sanderson | 31.01.13 | Discussion took place at meeting on 19th November to define the next steps | A |  |
|  | Develop a briefing note to ensure GPs and primary care providers understand their role and contribution to reducing the SHMI to be signed off by clinical leads in CCGs and shared with NLaG MD | James Tindall | Comms briefing to be developed by 31.12.12 To be agreed by SHMI Steering group Jan 2013 |  | G A |  |
|  | Development of primary care quality strategy & implementation plan for each CCG Output from Sustainable Services meeting in December to feed into discussions with the LAT | Peter Melton Margaret Sanderson | March 2013 Jan 2013 | NEL holding weekly meetings to develop primary care strategy NL meeting on 15 November to discuss | A G |  |
|  | Penalties to be added to contracts for never events for 2013 Agree content, trajectories and £ value Draft penalties to be agreed in NL Engine Room Forwarded to contract team for inclusion in contract discussion | Helen Kenyon Karen Rhodes/Zena Roberstson Karen Rhodes Karen Rhodes/Zena Roberstson | Penalties in acute contract for 2013/14 Feb 2013 January 2013 29.11.12 Jan 2013 | Raised requirement with HK commissioning lead to include in commissioning intentions. To include incremental penalties to encourage learning across organisation. | A A G A |  |
| Reducing patient harm requires both the proactive actions that reduce the risk of harm and reactive actions that review and learn from harm (or potential harm) that has occurred. It also requires triangulation, ie identifying those areas where concerns arise through more than one source. | Implement NHS safety thermometer throughout the Trust | K Dunderdale / Quality network | August 2012 | Implemented | G |  |
|  | Reduce delays throughout patient journey | A Smithson /P Wisher | Ongoing | Ongoing | A |  |
|  | Root cause analysis of SUIs and near misses | W Booth | Ongoing | Well established process | A |  |
|  | Implement WHO Surgical Checklist |  | A Smithson | Completed. Further briefing sessions run both in DPoW and SGH | G |  |
|  | OUTCOME 7 LEARNING FROM BENCHMARKING AND OTHERS |
| Request analysis from YPHO | Explore option of using PHO data. Task PH and Info leads to decide if sufficient information is available locally. | PH/Info group | September 2012 | Discussions with PH and Information leads suggest information already available from PH. | G | Benchmarking information to feed into SSP for future configuration. |
| Better and more regular data to monitor access to primary care Monitoring of referrals and consistency from primary care to reduce variation | Robust analysis of case-mix presenting to NLaG and comparison with peer group DGHs Debate with LAT to address variation and consistency Info/PH leads to present output at Dec SHMI Steering Group Indentify Variation Develop Plan to address variation | PH/Info group Cathy Kennedy Karen Rhodes Paul Twomey PH/Info group PH/Info group R JF & PM | Commence discussions with LAT January 13 January 2013 December 2012 February 2013 March 2013 | Information proposal to be taken to Nov 19th meeting and Information lead to attend meeting | G A A A A |  |
|  | OUTCOME 8 REDUCING BED OCCUPANCY |
| There is robust evidence that bed occupancy levels above 85% have an adverse impact on patient care. This is in part due to additional pressures on staffing levels, in part due to multiple patient moves and in part due to difficulties in cleaning thoroughly between patients. Much of the action required to reduce occupancy levels needs to be taken by commissioners and primary care, but there is also an important Trust role in ensuring that occupancy levels are kept as low as possible. | Minimise delays in patient discharge regardless of bed pressures | A Smithson/ CDs | Ongoing | Process in place Extensive bed reconfiguration in DPoW to Improve access and patient flows underway | G |  |
|  | Maintain bed occupancy rates at or below 85% for all wards at midnight 95% of days | A Smithson/ CDs | Introduce monitoring by October 12 |  | A |  |
|  | OUTCOME 9 LEARNING FROM PREVIOUS EXPERIENCE |
| Focussed review of the case note of patients who have died and when the use of the trigger tool identifies a possible issue will enable trends to be identified, causes for concern to be identified and addressed. This learning needs to be disseminated throughout the organisation along with the lessons from SUIs and near misses in a way that ensures practice changes. | Notes of all patients who have died to be reviewed using the trigger tool | L Blow/ coding team | Ongoing | Already implemented | G |  |
|  | All clinicians to be involved in review of case notes flagged for review by the trigger tool. Nurses to be part of the case note review. To establish nursing trigger tool and audit tool | E Scott/K Dunderdale | Ongoing | All consultants now involved. Trigger tool and audit form agreed. Nurses identified to review notes | G |  |
|  | Trigger tool and case note review trends, and specific cases to be discussed at Morbidity and Mortality meetings | E Scott/CDs | Ongoing | Surgical M&M well established, commencing in medicine | A |  |
|  | Better dissemination of lessons learnt from SUIs and M&M meetings | W Booth/ E Scott | Review of mechanisms for disseminating lessons learnt being reviewed – update to November Trust Governance Committee. Each group has also now confirmed the process for M&M meetings and how this information feeds in to the central mortality work | Ongoing | G |  |
|  | OUTCOME 10 IMPROVING PATIENT FLOWS THROUGH THE HOSPITAL |
| Ward to ward transfers are sometimes essential for high quality care – for example a patient who become unexpectedly more unwell may require transfer to intensive care, a patient found to have an infectious condition requires nursing in a single cubicle. But such transfers are distressing for patients and disrupt continuity of care. They are therefore to be avoided where possible and may impact upon mortality. The THL analysis showed that patients in DPoW who are subject to ward moves are more likely to do die than those who are not. This picture is not repeated in SGH; the reasons for this are not clear, but what is clear is that most of these transfers are driven by the pressures within general medical service. | Review general medicine patterns of service delivery | E Scott | November 2012 | Interviews completed, conclusions being linked into work being undertaken in medicine. | G |  |
|  | Monitor non clinical patient moves | A Smithson | October 2012 | Real time audit now being undertaken | G |  |
|  | OUTCOME 11 IMPROVING PATIENT PATHWAY |
| Commission models for end of life care which deliver consistent outcomes across Northern Lincolnshire and Goole communities | EOL groups to recommend outcomes and define model of care | Helen Kenyon Caroline Briggs Hilary Gledhill | Groups tasked by end of October 12 Recommendation on outcomes and model for 13/14 contracts Comms Plan by 31.12.12 |  | A | Understand impact of models and implications for home and community theme and integration of care themes of the new model and expected outcomes and the information system |
| Develop compliance monitoring system for use of LCP and Gold standards framework Develop integrated information system based on EOL registers NEL to ensure work already underway is completed and implemented to reduce delayed discharges | Comms plan to support Model & expected outcomes to be added into provider contracts Establish baseline position and develop action plans to demonstrate robust monitoring in place across health system Implementation of integrated information system NEL unscheduled care management group to oversee project to reduce delayed discharges | Caroline Briggs Helen Kenyon Supported by Lisa Revell Caroline Briggs Helen Kenyon supported by Lisa Revell Helen Kenyon | Baseline report on compliance monitoring end of November 12 Update report March 13 to mortality action group Update and recommendation on integrated information system by March 2013 October 2013 Unscheduled care issues to be resolved by March 2013 Progress report to mortality action group in December 2013 | NL - complete NEL - standards developed - monitoring not yet worked up | G A A A A G |  |
|  | OUTCOME 12 IMPROVING THE WHOLE PATIENT PATHWAY |
| Whilst the focus of this paper is the issues facing and actions required from NLAG, it needs to be recognised that this is a whole community issue and as such, requires actions from all organisations. These will need to be led by the commissioning organisations, but with the full participation and support of the Trust. These include improving end of life care, developing a safety culture in primary care, reducing delayed transfers of care and addressing variations in mortality rates between GP practices. |  |  |  |  |  |  |
|  | OUTCOME 13 IMPROVING THE QUALITY OF DATA, CODING AND INFORMATION |
|  | OUTCOME 14 IMPROVED DOCUMENTATION |
| Good documentation is an essential component of good patient care. This means that notes have to be available when they are needed, they have to be in good order so that information can be located rapidly and clinical entries need to be thorough yet concise, appropriate and legible. Information also needs to be recorded in a way that enables the coding team to code accurately and comprehensively. The introduction of electronic patient records is a great opportunity and there needs to be a careful process of ensuring that the electronic system is designed to meet all the needs of the different clinical and administrative teams. Equally, it must also be recognised that implementation of electronic records will take time and steps must be taken in the interim to improve the quality and availability of medical records. | Clinicians to use note finding team when records not available | CDs | Ongoing Started |  | A |  |
|  | Audit of non availability of notes | K Wilson | November 12 | Not yet started | R |  |
|  | Standards of documentation to be set for all medical and nursing teams and expand the use of care bundles | E Scott/CDs/K Dunderdale | November 12 | Underway & will be ongoing | A |  |
|  | Use of co-morbidities form to be monitored within performance dashboard | J Daws | October 12 | Implemented | G |  |
|  | CDs to tackle teams not using co-morbidities form | CDs | October 12 | Information not yet available | R |  |
|  | Co-morbidity form to be incorporated onto Web-v | P Wisher | November 12 | Agreement reached on incorporation | G |  |
|  | OUTCOME 15 IMPROVED CODING |
| Better medical records will undoubtedly improve coding, but there still needs to be a good working relationship between the coding and clinical teams, with direct clinician involvement in the coding process. This will help clinician and coder understanding of the coding rules and improve the quality of information as a consequence. However we also need to learn from other organisations to see if the way that we interpret the coding rules can be improved. | All clinicians involved in coding sign off | E Scott/CDs | Ongoing | Started | G |  |
|  | “Query” diagnoses reduced | CDs/L Blow | Ongoing | Started. Coding for “impression” changed, coding of “R” codes reducing as coders increasingly searching for clinical information. Review of missed co-morbidities underway | G |  |
|  | Visit exemplar sites | L Blow | November 12 | Not yet started | R |  |
|  | OUTCOME 16 IMPROVING OUTCOMES |
| Utilise (Paul Twomey's) analysis already undertaken to inform action plan (Mortality Analysis & Paul's report + 3 appendices - Cathy Palmer e-mail refers) | Analysis to be reviewed and action plan updated Task PH/Information group (Martin Rabetts) to develop further recommendations on actions | Zena Robertson Karen Rhodes | 31.01.13 |  | A |  |
| Commissioners to draw up an out of hospital action plan Explore mechanisms for monitoring deaths out of hospital in real time Commissioners to set clear quality outcomes for providers | Plan to be developed after quality summit in October Stage 1 develop model of out of hospital care Stage 2 development of a primary care quality strategy To be developed linking into the new coroner system Outcomes to be put into provider contracts with associated incentives and penalties for 13/14 CSU to review and identify pertinent elements for inclusion within commissioning Intentions from the NHS Quality outcomes framework for 13/14 contract | Zena Robertson Karen Rhodes PM & MS Cathy K & KR Peter Melton Robert JF Helen Kenyon/Caroline Briggs/ Alex Seale Caroline Briggs & Helen Kenyon | 31.12.12 31.01.13 28.02.13 Initial scoping on real time monitoring by April 13 31.01.13 31.12.12 | NL have a meeting on 15th November to discuss NEL have weekly meeting through November and December to develop model All deaths in GP practices to be reviewed as per Peters discussions. PM and RJF to ensure all practices participate | A A A A A R | Consider the out of hospital action plan for SSP configuration |
|  | OUTCOME 17 IMPROVE OUTCOME BASED INFORMATION |
| There is a wealth of information available, but it is not always easily accessible or interpretable. A mortality information product needs to be designed, refined and further refined so that a wide range of people have easy access to the information they need, without repeated one off requests to the information team. There is also a need for more immediate information. The SHMI is by the nature of its design always between 6 and 18 months out of date, and the RAMI also several months out of date. Whilst these indices are more meaningful as they are standardised, they can and should be complemented by the publication of monthly crude mortality rates. | Revise mortality related information products | J Daws/ S Hearn | November 12 | Started. Format changed on feedback received. | G |  |
|  | Publish monthly crude mortality rates | S Hearn /J Howden | September 12 | Completed | G |  |
|  | OUTCOME 18 BETTER ANALYSIS OF AVAILABLE DATA |
| The analysis undertaken by THL demonstrated that more learning could be gleaned from the available information. Resource has been identified to undertake further analysis; it will be important to monitor the extent to which this analysis can be undertaken by existing staff and the extent to which this will need to be brought in. In particular, there needs to be a much better understanding of the reasons for the higher than expected mortality rates for patients with a lower risk of dying as reported by THL. | Further analysis of trends over time and differences between sites | S Hearn | October 12 | Started | G |  |
|  | Further analysis of patient risk groups | S Hearn | November 12 | Analysis undertaken in several areas including weekend mortality. | G |  |
|  | Review of analytical resource | E Scott/ J Howden | Ongoing | Initial review completed, but will be ongoing | A |  |
|  | OUTCOME 19 RAISING THE PROFILE OF ACTION TO REDUCE MORTALITY |
| Mortality is obviously an important element of quality of care. However, in order to give proper focus to mortality related issues without distracting form the patient experience issues, a monthly report will go to the Quality and Patient Experience Committee and to the Board to report on progress in reducing the SHMI and RAMI. | Present monthly mortality report to QPEC and the Board | E Scott | September 12 | Completed and ongoing | G |  |
|  | PUTCOME 20 DEVELOPING A QUALITY CULTURE |
| With any cultural change, visible and effective Board leadership is essential. | Board workshop to review mortality action plan | Board members | August 12 | Completed | G |  |
|  | Ensure proper consideration is given to mortality by the QPEC | QPEC membership | September 12 | Completed and ongoing. QPEC meeting dates reviewed to facilitate due diligence | G |  |
| NEXT STEPS The Executive Team have recognised the size of the task facing the Trust if it is to reduce its mortality ratios to below those of its peers. Accordingly, a dedicated team has been identified to support the Medical Director. This team will have as its first task a review of all the actions identified in this paper and the Transforming Health paper so that all actions necessary can be taken. |  |

| Report Action | Detailed action | Lead Director | Timescale |  | Progress update | RAG | Sustainable services impact |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | OUTCOME 21 STAFFING CAPACITY AND CAPABILITY |
| Develop the capacity for undertaking implementation phase of mortality action plan | Establish additional commissioner capacity to deliver the required pace and assurance on improvement & implementation Additional information & analytical capacity | Zena Robertson Karen Rhodes Hilary Gledhill | Capacity identified by 19th November November 2012 |  | Secured additional resources Ad hoc Info & Public Health Group established | G G |  |
|  | OUTCOME 22 CULTURE AND OD CHANGE |
| Joint meetings developed in NL and at practice level in NEL Commissioner and provider clinical forward programme to be developed | Commissioners to ensure that respective provider networks are established and TOR agreed Provider networks to be established and TOR written at NL/NEL & Goole Forward programme to be established | Cathy Kennedy Allison Cooke Margaret Sanderson Peter Melton & Liz Scott | 31.12.12 To be agreed by January 2013 |  | NEL primary care network established ToR required. Provider network ToR as per LS discussions | G A |  |
|  | OUTCOME 23 IMPROVING PUBLIC CONFIDENCE |
| Report to go to SSP CSG Retain SHMI steering group to oversee improvement Implementation of SHMI action plan and trajectory for improvement within appropriate timescales | Report to September CSG Revise membership & TOR Develop and monitor system wide action plan Commissioners to oversee and assure timely implementation of the system action plan | Sue Rogerson Peter Melton | Completed Completed On-going Action plan to be completed & trajectory achieved by end October 2013 |  |  | G G A | Sue Rogerson SSP Director now part of the SHMI group |

# Text boxes

Attachment 6