## Slide 1: Healthy Lives, Healthy Futures NEL Partnership Board update
13th November 2014

## Slide 2: HLHF Progress Oct – Nov
We have...
  Undertaken work to assess our financial challenge and understand the impact that current plans will have
  Collated the feedback from the public consultation on Hyper –Acute Stroke and ENT inpatient surgery
  Responded to local Overview and Scrutiny Committees
  Communicated feedback to Council of Members at both CCG’s
  Re-assessed operational programme arrangements to focus on support for local delivery whilst recognising that some workstreams need a joint approach

## Slide 3: Current Position
Locality projects across Northern Lincolnshire have been mapped to the funnel, and reviewed against expected financial savings.
The financial gap “do nothing” position has been reassessed, based on updated assumptions. The likely position is £104m across the whole health community.
The current CIPs and Schemes amount to an expected £56m benefit which leaves a gap of £48m.
Gap of £104m

## Slide 4: Scheme Management
Locality projects across Northern Lincolnshire will be managed locally to ensure delivery of:
Increased levels of self-care and independence
Increased care delivered in the community, either in patient homes or community locations
Reduced outpatient reviews
Reduced A&E attendances
Reduced hospital admissions
This will deliver a step-change in the volume of hospital care that is needed locally.
This reduction in acute “contacts” will be quantified and a local vision for acute care over the next 5 years will be developed by Jan 2015.

## Slide 5: Programme Portfolio
NL Locality schemes
BCF, Frail & Elderly
NEL Locality schemes
12 priority schemes
Urgent Care Whole System Vision
Healthy Lives, Healthy Futures Service Delivery Strategy
Business as usual
CIPs / QIPPs
The HLHF Financial Model – outlining impact of all schemes and quantifying the vision
Enabling workstreams: Estates, IT Strategy, Transport, Communications & Engagement

## Slide 6: Key Elements of the next phase
Implementation of key enabling work that does not require formal public consultation
Development of a clinically driven Healthy Lives, Healthy Futures service delivery strategy
On-going engagement with key stakeholders, clinicians and the public
Formal public consultation as required, dependant upon changes being considered as part of the delivery strategy