North East Lincolnshire CCG

| Report to: | NEL CCG Partnership Board |
| --- | --- |
| Presented by: | Helen Kenyon, Deputy Chief Executive |
| Date of Meeting: | 9 January 2014 |
| Subject: | NELCCG/NELC Partnership Agreement Business Plan Progress Update |
| Status: | OPEN CLOSED |
| Agenda Section: | STRATEGY COMMISSIONING OPERATIONAL ISSUES |

| OBJECT OF REPORT |  |
| --- | --- |
| As part of the strategic agreement between the CCG and the Council it was agreed that the Business Plan for the period 2013-16 it was agree that rather than get into a process of producing a lengthy and detailed document with multiple actions for each organisation to deliver against, the partners would identify a small number of strategically important / high level priorities that both organisations would need to contribute to / work on together to deliver. The outcome of the work in year one of the business plan sets the priorities for delivery in year 2 and 3. The Strategically important / high level priorities identified for progress in the current year were: The Vulnerable Peoples Outcome Review Reviewing the Transitions arrangements between children’s and adults Social Care Further development of the partnership arrangements in place between the CCG and Council Development and Delivery of the “Local Account” This report provides a progress update on the progress made in relation to the work priorities for the current year. |

| STRATEGY |  |
| --- | --- |
| Partnership working is a key enabler identified by the CCG and the Partnership Agreement entered into by the CCG and the Council is of strategic importance to the CCG if it is to deliver against its vision of delivering “Joined up Solutions”. Under the partnership agreement the Council has delegated responsibility for Adult Social Care Commissioning to the CCG, and the CCG has delegated responsibility for Children’s Health Commissioning, 5-19. to the Council |

| IMPLICATIONS |  |
| --- | --- |
| If the CCG and Council fail to work effectively together then neither organisation will deliver against their agreed priorities, and services could become disjointed and fragmented leading to gaps in service provision. |

| RECOMMENDATIONS (R) AND ACTIONS (A) FOR AGREEMENT |
| --- |
|  | The Partnership Board are asked to note progress against the priorities 2013/14 priorities. | Agreed? |

|  |  | Yes/No | Comments |
| --- | --- | --- | --- |
|  | Does the document take account of and meet the requirements of the following: |  |  |
| i) | Mental Capacity Act | No |  |
| ii) | CCG Equality Impact Assessment | No |  |
| iii) | Human Rights Act 1998 | No |  |
| iv) | Health and Safety at Work Act 1974 | No |  |
| v) | Freedom of Information Act 2000 / Data Protection Act 1998 | No |  |
| iv) | Does the report have regard of the principles and values of the NHS Constitution? www.dh.gov.uk/en/Publicationsandstatistics/Publications/PublicationsPolicyAndGuidance/DH_113613 | Yes | Under “Principles that Guide the NHS” item 5 states: The NHS works across organisational boundaries and in partnership with other organisations in the interest of patients, local communities and the wider population. |

North East Lincolnshire CCG & Council Partnership Agreement priorities for the period 2013-16

| Strategic / High Level Priority | Overview of the work required in Year (2013/14) | Lead and support Arrangements | Progress against the 2013/14 work required | Work required 2014-16 |
| --- | --- | --- | --- | --- |
| The Vulnerable Peoples Outcome Review | Development of Business Case(s) to identify where the required £7m savings could be made by ASC to support the council in achieving its Medium Term Financial Plan requirements | Overall Lead for the Vulnerable adults Review- Bev Compton CCG Lead - Helen Kenyon Technical support - Geoff Lake | Business case developed which has been through the Council process (scrutiny) for agreement. Agreement reached about the phasing of the money coming out of the system, will be managed to enable the council to achieve its savings requirements within the required timescale, whilst enabling the CCG to deliver the service changes in a safer timescale. A high level delivery plan has been produced & a more detailed implementation plan is being produced through the CCGs Financial Programme Group | Implementation of the agreed plans to generate the savings required within the timescale agreed |
| Reviewing the Transitions arrangements between children’s and adults Social Care | To undertake a review of the current Transitions arrangements and develop a new process that will include Adult Social care in the planning process to better control the costs for the council | Overall Lead – Joanne Hewson Supported by Angie Walker | Review of current transitions process undertaken, and revised process developed which include ASC as part of the planning process. Review audit of the difference made as a result of the changes needs to be undertaken as part of the year 2 plan, when the changes have been fully implemented. | Implementation of the agreed processes and continuous review |
| Further development of the partnership arrangements in place between the CCG and Council | To identify further areas where working in partnership between the CCG and Council would be of benefit. This work would be in part driven by the production of an expression of interest for NEL to become an Integration Pioneer | Overall lead for each organisation Peter Melton & Tony Hunter Supported by Helen Kenyon & Liz Jones | Pioneer Bid submitted, but was not successful in being chosen. As part of the changes to management arrangements and the closer working between the CCG & council, the following areas where closer working would be beneficial have been identified for early progress: Children’s commissioning – a Strategic Commissioning Lead with a clinical background has been appointed as a joint post to support the development of the strategic plan for childrens services as part of Healthy Lives Healthy Futures (HLHF). Working with the Voluntary sector. A joint piece of work is to be undertaken to ensure a consistent way of working with the voluntary sector that ensures they are supporting & being supported to help deliver against the CCG/Council strategic imperatives Transport. Work is starting in relation to a review of the transport service in NEL. Transport has been identified as a major factor as part of the CCGs HLHF engagement process, and as a area where efficiencies can be made within ASC. Other areas for greater joint working will continue to be identified and progressed through the leadership group meetings. | Implementation of the further areas identified for joint working |
| Development and Delivery of the “Local Account” | To produce the “Local Account” in accordance with the timescales prescribed by ADASS | Overall lead for the production of the Local Account – Jake Rollin Supported by Bev Compton | The Local Account for the year ending 2012/13 has been produced in accordance with required timescales. A draft of the report was submitted to ADASS for review and comment, & amendments made to the final report where appropriate. A comprehensive response to the comments made by ADASS was sent back to them. The document has been to the Councils Portfolio Holder meeting for sign off and has also been sent to the CCGs Delivery Assurance Committee. The document has been uploaded on to the CCGs website, link attached for info to the document. http://www.northeastlincolnshireccg.nhs.uk/local-account-for-adult-social-care-launched/ Work has already commenced on how the process and document can be improved for the coming years account production | Further refinement of the document in line with feedback from the public and best practice learning via Regional ADASS leads. |

# Text boxes

Attachment 7