North East Lincolnshire CCG

| Report to: | NEL CCG Partnership Board |
| --- | --- |
| Presented by: | Paul Kirton-Watson Strategic Lead- Quality & Experience |
| Date of Meeting: | Thursday 9th January 2014 |
| Subject: | Final update on Keogh Review |
| Status: | OPEN CLOSED |
| Agenda Section: | STRATEGY COMMISSIONING √OPERATIONAL ISSUES |

| OBJECT OF REPORT |  |
| --- | --- |
| The CCG Governing Body are asked to note the recommended actions submitted by North Lincolnshire and Goole Foundation Trust [NLAG] against the recommendations and issues raised within the Keogh report of July 2013. It is noted that the Governing Body had sight of the relevant Keogh report documents at the November 2013 meeting. This report provides more detailed information to the board to inform them of the level of assurance currently presented by NLAG as part of their assurance framework. A final visit by the Keogh team was made to NLAG in the Autumn of 2013. The visiting team found that considerable improvements had been made in terms of progress against the action plan In particular, significant progress has been made in terms of: Improvements to the main hospital sites to the pathway of care for stroke patients Strengthened the clinical leadership within NLAG including the appointment of a new Medical Director ( in post w/c 6/1/14),implementing a revised clinical leadership structure with effect from January 2014 Strengthened the way deteriorating patients are recognised and monitored by rolling out the NEWS ( National Early Warning Scoring system) Improved the flow of patients from admission to discharge – including changes to the management of the Medical Admissions Unit and the launch of the Surgical Assessment Unit Strengthening the nursing workforce by employing a number of overseas nurses Improved compliance with mandatory training and appraisal Increased the visibility of Board Members and the introduction of Director Forums where staff can engage directly with Board Members to raise concerns in respect of quality or other issues and also to share good practice and innovation. |

| STRATEGY |  |
| --- | --- |
| Quality is one of the CCGs key priorities and higher than expected mortality rates are an indicator that the quality of care may not be being delivered to a standard that the CCG would expect. |

| IMPLICATIONS |  |
| --- | --- |
| The fact that our local provider was identified as a provider to be part of the Keogh review is a strong indicator that the quality of care locally is not where we would want or aspire for it to be. As a result of the Keogh review there will be changes to service which affect our local population, which will need careful consideration and management. Since the visit of the Keogh Team, NLaG have produced detailed action plans ( see attached) to enable them to progress with the key areas that the Keogh Team identified as needing improvement. The Executive Team at NLaG have monthly meetings with Monitor to ensure they comply with conditions set out in the Licensing Agreement. The enclosed detailed action plan has been submitted by NLAG to address the Keogh recommendations. It is the current action plan and is detailed, although work in progress, it demonstrates the organisation is making steady progress against the Action plan produced after the initial Keogh visit. The enclosed list of key performance indicators have been developed by NLAG and will be reported upon through the Contracting Monitoring Board. |

| RECOMMENDATIONS (R) AND ACTIONS (A) FOR AGREEMENT |
| --- |
|  |  | Agreed? |

|  |  | Yes/No | Comments |
| --- | --- | --- | --- |
|  | Does the document take account of and meet the requirements of the following: | √ |  |
| i) | Mental Capacity Act | √ |  |
| ii) | CCG Equality Impact Assessment | √ |  |
| iii) | Human Rights Act 1998 | √ |  |
| iv) | Health and Safety at Work Act 1974 | √ |  |
| v) | Freedom of Information Act 2000 / Data Protection Act 1998 | √ |  |
| iv) | Does the report have regard of the principles and values of the NHS Constitution? www.dh.gov.uk/en/Publicationsandstatistics/Publications/PublicationsPolicyAndGuidance/DH_113613 | √ |  |

Keogh Review

Background to the Keogh Review

On 6th February the Prime Minister announced that he had asked Sir Bruce Keogh to review the quality of care and treatment provided by those NHS trusts and NHS foundation Trusts that were persistent outliers on Mortality indicators.  14 hospital trusts were identified for review and Northern Lincolnshire and Goole Hospitals NHS Trust (NLG) was one of the 14.

The reviews sought to determine whether there are any sustained failings in the quality of care and treatment being provided to patients at the 14 trusts & identify:

- Whether existing action by these trusts to improve quality is adequate and whether any additional steps should be taken

- Any additional external support that should be made available to these trusts to help them improve

- Any areas that may require regulatory action in order to protect patients.

Methodology and Approach

A 3 stage approach was adopted for the reviews:

Stage 1 - Gathering and analysing the full range of information and data available within the NHS to develop key lines of enquiry.

Stage 2 – A Rapid Responsive review where a team of experienced clinicians, patients, managers and regulators, go into each hospital and observe the hospital in action.  This involved walking the awards and interviewing patients, trainees, staff and the senior executive team.  This stage included both an announced and an unannounced visit to each Trust

Stage 3 - A Risk Summit, where a summary of the findings from the rapid responsive review were discussed and recommended actions deliberated & agreed.

Northern Lincolnshire and Goole Hospitals Specific review

NLG were in the second wave of trusts to be reviewed and their announced visit started on the 5th June 2013 at Diana Princess of Wales Hospital, continued on the 6th June 2013 at Scunthorpe District General Hospital & then concluded on the 7th June 2013 at Goole Hospital.  Their unannounced visit was made out of hours on Friday 14th June to Diana Princess of Wales Hospital.

The Key Lines of Enquiry within four Theme areas were agreed by the panel as:

Theme	Key Line of Enquiry

Governance and leadership

- Can the Trust clearly articulate its governance process for assuring the quality of treatment and care?

- How does the Trust use information locally?

Clinical and operational effectiveness

- What governance arrangements does the Trust have to monitor and address clinical and operational performance data at a senior level?

- How does the Trust ensure consistency across its sites?

Patient experience

- How does the Trust engage with patients, their family and carers?

Workforce and safety

- In the context of this review, can the Trust describe its workforce strategy?

- How is the Board assured that it has the necessary workforce deployed to deliver its quality objectives?

- What assurance does the Board have that the organisation is safe?

The stakeholder summit took place on Friday 5th July, with the Rapid Responsive Review Report being published later in July, once each of the 14 trusts stakeholder summit had taken place.

A report summarising the findings and actions arising from the 14 investigations, the 14 individual trusts rapid responsive review reports and the individual trusts agreed action plans have all been published on the NHS Choices Website:

www.nhs.uk/NHSEngland/bruce-keogh-review/Pages/published-reports.aspx

Each recommendation made in the review was rated:

- Urgent – the trust should take immediate action to respond to the recommendation and ensure improvement in the quality of care

- High – the trust should develop a response and action plan for these recommendations to ensure improvement in the quality of care

- Medium – The trust should implement these recommendations to ensure on-going improvement in the quality of care.

In total the trust received 18 recommendations categorised as Urgent, 39 as high and 24 as medium.

The Rapid Responsive Review Report provides a detailed analysis of the panels finding, but also summarised the findings into four key areas of concern, for the trust to focus on to improve the quality of care, patient safety and experience.

Within the report the Panel also noted a number of areas of good practice or planned improvements, which were also noted in the report, including: the planned move to advanced 7 day working in diagnostics, the implementation of the National Early Warning Scores (NEWS) for monitoring patients.  The Report also noted that there was evidence of good visibility of the Chief Executive and Chief Nurse.

The 4 key areas of Concern highlighted were:

- Inadequate progress being made to improve the quality of services with pace utilising effective clinical leadership

Within this area the Panel was particularly concerned that the Trust is not yet offering thrombolysis treatment for stroke patients after hours at both sites and that the Trust needed to work with the Clinical Commissioning Groups (CCG) to address this urgently. It was recommended that the Trust conduct an urgent review of the out of hours stroke services at Diana, Princess of Wales Hospital and implement recommendations, agreed with the CCG, by the end of July 2013.As of November 2013 ,Hyper-acute stroke services for North East Lincolnshire residents are now being delivered at Scunthorpe General Hospital

- Poor patient flow management, lack of early triage, multiple bed moves and poor management of outliers, particularly at the Diana, Princess of Wales Hospital

Within this area the panel observed effects of inadequate capacity and poor patient flow management throughout the emergency and acute pathway, as well as in theatres and on surgical wards, most acutely at the Grimsby site.

- Inadequate staffing levels, quality and skill mix in a number of areas

At the unannounced visit in Grimsby, the panel observed inadequate nurse staffing levels and leadership to cope with clinical demand in A&E, Medical Assessment Unit (MAU) and the medical wards.  The panel also observed gaps in handover and in middle grade and senior medical involvement out-of-hours

- Evidence of poor care and patient experience in some areas

Within this area it was noted that the Trust was using interpretations of the single sex accommodation standards in certain areas of the Trust which are no longer deemed acceptable. The panel observed mixed sex accommodation breaches, relative to standards applied nationally, in the stroke wards in both Grimsby and Scunthorpe and in the MAU and Intensive Care Unit (ICU) in Grimsby.

A commissioner led visit to the Diana Princess of Wales Hospital was undertaken on 12th September 2013, a number of wards and Departments where visited, the visiting team observed clinical practice and took to opportunity to speak with a number of clinical staff who were able to amplify the Core Values of the organisation, along with the Chief Nurses Strategy.

A number of patients and visitors were spoken to who spoke very positively about the quality of care they have received.

Action Subsequent to the Review

In preparation for the Risk Summit NLG were required to produce an action plan.  Following the publication of the report Monitor announced that it was going to place a number of trusts which has been subject to a Keogh review into special measures in order to “fix” failings in patient care or the way the hospital is run.  NLG was one of the trusts placed into special measures.  This means that NLG has been issued with an additional licence condition & enforcement undertakings in relation to the recommendations contained within the Keogh report.

NLG are therefore required to report to monitor as required, but at a minimum monthly to assure the regulator that they are making progress towards implementing the action plan within the required timescale.

The Trust have  strengthened their governance and reporting arrangements to improve the oversight of progress made by the trust, both in terms of implementing the Keogh and SHMI action plans via the establishment of a Mortality Performance Committee, which together with the Quality & Patient Safety Committee report into the Board.

Attached for information is the latest copy of the Trust Boards Keogh Action Plan progress report, which provides an update against the Trusts Keogh Action plan and confirms the governance and assurance arrangements in place to support delivery of the agreed actions.

In an effort to improve clinical care and staffing levels, a number of nurses from Spain have been recruited by the organisation and are currently undergoing a comprehensive programme of induction prior to commencing work in clinical areas.

The Trust has commissioned KPMG to undertake an independent assessment of the sufficiency and deliverability and of their Keogh Action plan.

Each of the actions detailed within the plan have been assessed as either:

- Completed by the deadline

- On target for completion by the deadline

- Not completed by the deadline / overdue.

The Commissioners, through the CSU have requested that they undertake a review of the action plan, to both provide an assurance to the CCGs that the trust plan is robust, but also to identify where they may have been any contract breaches that would require action.   On an on-going basis the commissioners have agreed that they will oversee the implementation of the Keogh Action Plan via the Contract Quality Group, with escalation as required to the Contract Board (Chaired by the CCGs Deputy Chief Executive or NLCCGs Senior Officer – Commissioning).

In addition it has been agreed that a Clinical Board to Board Meeting be held between the commissioners and NLG.  This meeting took place on 17th December 2013.  The purpose of this meeting was to bring all organisations to the same level of understanding in relation to the detail of the plan, progress in relation to implementation of the plan and to provide assurance to the CCGs that NLG are implementing changes that will improve patient care at an appropriate pace.

# Text boxes

Attachment 10a