**North East Lincolnshire CCG & Council Section 75 and Partnership Agreement priorities for the period 2016/19**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Section 75 Priorities** |  |  |  |  |
| **Strategic / High Level Priority** | **Work Required 2016/17** | **Work required 2017/18** | **Work required 2018/19** | **Lead** |
| Adult Social Care : | Delivery of the final year of the current ASC savings plan  Prepare for the ASC Peer Review  Develop and implement an action plan to any recommendations arising from the Peer Review  Review & develop the Residential care contract, including the quality framework.  Develop and implement the support to nursing and residential care project (proactive / planned care)  Develop plans to support the domiciliary care provider resilience | Implement new monitoring arrangements in line with revised Residential care contract and quality framework  Review and amend support to nursing and residential care project based on findings from initial work.  Develop and commence training for residential following learning from the support to residential care project  Implementation of domiciliary care development to ensure provider resilience | Develop the support to nursing and residential care project to make it appropriate to supporting those individuals within the community who have been identified as at high risk of deterioration. - top 2 % | Helen Kenyon  Bev Compton  Bruce Bradshaw/Nic McVeigh  Bev Compton |
| Children: | Extension of the CAMHS contract to enable work to be completed by the childrens and adult mental health commissioner to determine the most appropriate mechanism to secure Mental health services going forward. i.e. separate procurements for childrens and adults MH services or procurement for an all age MH service  Review of the Childrens Partnership Board to ensure fitness for purpose going forward  Development of the 0-19 Programme  Review and refresh maternity commissioning intentions in light of the recommendations within the national review of maternity services | Undertake procurement for MH services in accordance with the decision taken in 2016/17 re the procurement span  Implementation of the 0-19 Programme  Ensure providers of maternity services are meeting the requirements of the recommendations within the National review. | Contract mobilisation and work with the provider to ensure that services are imbedded  Implementation of the 0-19 programme | Joanne Hewson  Michelle Barnard  Lauren King  Joanne Hewson  Steve Kaye  Michelle Barnard |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Wider Partnership Priorities |  |  |  |  |
| **Strategic / High Level Priority** | **Work Required 2016/17** | **Work required 2017/18** | **Work required 2018/19** | **Lead** |
| Strategic Commissioning | Development of the strategic commissioner for place, to provide a strong single voice for NEL which is able to shape and influence:   * local service provision * STP * Devolution etc.   Development of a single Outcomes Framework for NEL  Development of the Health and Wellbeing Board to become the commissioning forum for place  Support the development of the ACP within NEL to ensure fitness for purpose to deliver against the required outcome measures – Strategic commissioner to develop the fitness for purpose test assurance process for the ACP | Commence commissioning in accordance with the agreed outcomes framework  Streamline processes between the council and CCG to ensure that providers a single contract that covers all services it is required to deliver on behalf of the council & CCG.  Continued development support to the ACP | Review progress towards delivery of the outcomes framework | Cathy Kennedy  Joanne Hewson  Stephen Pintus  Helen Kenyon |
| Improving the health and wellbeing of the public | Development and adoption of a Preventative framework, to support strategic commissioning of services  Identify priority areas for commissioning for prevention for inclusion in the 2017/18 & 18/19 planning round | Assess progress against implementation of the preventative framework. | Identify priority areas for commissioning for prevention for inclusion in the 2019/20 planning round | Stephen Pintus |