## Sheet1
Stage | Action Required | By Whom | By When | Update
Initial Planning | Produce high level specification/ principles | HK/ DrS | 31.07.15 | Completed
| Develop clear outcomes guidance (with minimum requirements) | HK/ DrS | 31.08.16 | Completed
| Secure Laptops to be utilised to support the project within Care Homes | JL | 31.03.15 | 40 Laptops secured - awaiting feedback from IT regarding their deployment. May need to acquire additional laptops to cover the 3 remaining homes.
| Develop detailed specification | NM | 31.08.15 | Completed
| Gain agreement of specification | HK/ DrS | 03.09.15 | Completed
| Workshop to develop next steps | HK/ NM | 08.10.15 | Completed
| Establish Implementation Group | NM | 30.10.15 | Completed
| Understand the SIPS currently in place which would support the project, including resources and timescales. | DW | 30.11.15 | Completed
| Research Vanguard sites and others areas implementing similar initiatives | NM | 30.11.15 | Completed
| Liaise with Primary Care to understand the number of individuals in their "Top 2%" | NM | 31.12.15 | Partially completed - some information still missing from surgeries.
| Agree implementation plan and timescales | NM | 22.01.16 | Partially completed
| Understand the professional input into Care Homes, utilising signing in sheets from Care Homes and professionals' diaries for the week Monday 7th December – Sunday 13th December inclusive. | All | 31.01.16 | Partiallly completed
| Engage with Stakeholders (Care Homes) regarding the project and seek their sign up and inclusion in the project | NM | 27.01.16 | Stakeholder event completed - working to engage all LTC Providers.
| Understand all of the SIPS in place and the implications if any of the project on these SIPS moving forward | NM | 29.02.16
| Gain sign off for the implementation plan at Council of Members | NM | 04.02.16
Implementation Phase One | Recruit a Team Leader | NM | 31.03.16
| Recruit an Administrator | NM | 31.03.16
| Gain agreement to align Social Workers to each Care Home | CJ/ NM | 29.02.16
| Gain agreement to align Mental Health Workers to each Care Home | AB/ NM | 29.02.16
| Gain agreement to align Therapists to each Care Home | CH/ NM | 29.02.16
| Gain agreement to align Nurses to each Care Home | DA/ NM | 29.02.16
| Gain agreement to align Pharmacists to each Care Home | RS/ NM | 29.02.16
| Work to align all agreed professionals to each Care Home | NM | 31.03.16
| Agree methods of working - roles, responsibilities, joint working | ALL | 31.03.16
| Establish the training requirements of Care Home staffing | ALL | On-going
| Launch Phase One | ALL | 01.04.16
| Deliver Phase One - MDT coordinated and consistent response, Care Homes Training etc. | ALL | 01.04.16-31.03.19
Implementation of Phase Two | Work to develop the Crisis/ Emergency response model including all MDT professionals | ALL | 30.09.17
| Implement the Crisis/ Emergency response model covering 7 days working with OOHs | ALL | 01.10.17
Evaluation of Phase One & Two | Full evaluation of Phase One and Two | ALL | 01.04.18-30.06.19
Implementation of Phase Three | Roll out of the model, adapted appropriately to meet the top 2% of users across the system in NEL. | ALL | 01.04.18
Evaluation of Phase Three | Full evaluation of Phase Three concluded | ALL | 31.03.20