| PURPOSE OF REPORT: | To update the Partnership Board on progress and slippage towards achieving the objectives set out in the CCG’s Corporate Business Plan. For sections where all actions/milestones are complete, there is simply a percentage progress bar. Detailed sections represent exceptions (where milestone dates have been missed or actions not completed. |
| --- | --- |
| Recommendations: | For the Partnership Board to note progress and exceptions towards delivery of the 2017/18 Corporate Business Plan |
| Sub Committee Process and Assurance: | The Corporate Business Plan is overseen by the Delivery and Assurance committee and reviewed regularly at each of its meetings. |
| Implications: |  |
| Risk Assurance Framework Implications: | The Delivery and Assurance Committee reviews the Corporate Business Plan and any associated risk on a regular basis |
| Legal Implications: | None identified |
| Equality Impact Assessment implications: | No |
| Finance Implications: | No specific issues in relation to the report however some of the slipped actions may affect subsequent savings assumptions should the position not be recovered. |
| Quality Implications: | There are some specific actions around quality with some minor slippage – further details are in the attached report |
| Procurement Decisions/Implications (Care Contracting Committee): | Not applicable |
| Engagement Implications: | Relevant specific actions(service improvements) will require engagement during 17/18 and these are built into the Corporate Action Plan where relevant |
| Conflicts of Interest | None |
| Strategic Objectives Short summary as to how the report links to the CCG’s strategic objectives | Sustainable Services The Corporate Action Plan is designed to support all of the strategic objectives of the organisation |
|  | 2. Empowering People The Corporate Action Plan is designed to support all of the strategic objectives of the organisation |
|  | 3. Supporting Communities The Corporate Action Plan is designed to support all of the strategic objectives of the organisation |
|  | 4. Delivering a fit for purpose organisation The Corporate Action Plan is designed to support all of the strategic objectives of the organisation |
| NHS Constitution: | Does the report and its recommendations comply with the requirements of the NHS constitution? Yes |
| Report exempt from Public Disclosure | No |

| Appendices / attachments |  |
| --- | --- |

| Corporate Action Plan 2017/18 Generated on: 29 June 2017 |  |
| --- | --- |
| Action Title | Progress |
| Delivering a Fit for Purpose Organisation |  |

| Action Title | Progress |
| --- | --- |
| Structure |  |

| Action Title | Progress |
| --- | --- |
| Systems & Processes |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Establish systematic financial planning and approval of bids etc across STP | Laura Whitton |  | Robust financial plan (STP, NEL locality & NEL CCG) NEL locality finance bids appropriately considered as part of the overall STP System in place to maintain a “live” version of the plan | Complete plan | 28-Apr-2017 | Yes | Initial plan completed |
|  |  |  |  |  | STP plan signed off by NHSE | 30-Jun-2017 | No | Formal sign off from NHSE yet to happen due to North Lincs system financial gap. Sign off will be done via the CEP process – due to be completed in June 17. |
|  | Look at the purpose and aims of the sub-committees of the Board | Jan Haxby; Helen Kenyon; Laura Whitton |  | Achieve clarity on the purposes of each of the sub-committees of the Board Board in an attempt to: avoid duplication of assurance processes ensure there are no gaps in assurances ensure performance and quality is not seen in silo | Care Contract Committee - review ToR - Helen | 30-Jun-2017 | Yes | Has been reviewed no changes required |
|  |  |  |  |  | Delivery Assurance Committee - review ToR - Helen | 30-Jun-2017 | No | Meeting taking place to look at overlap and duplication between DAC and Quality Committee – discussions ongoing |
|  |  |  |  |  | Information Governance and Audit - review ToR - Laura | 30-Jun-2017 | No |  |
|  |  |  |  |  | Review current structure and propose a revised structure of sub-committees based on new partnership arrangements with NLEC and the implications for NEL CCG | Nov 2017 | No | Meeting has taken place to discuss the opportunity for bringing performance and quality monitoring into 1 place/meeting. this was considered a good idea but requires more consultation and consideration of the future partnership arrangements with NELC |

| Action Title | Progress |
| --- | --- |
| Management Style |  |

| Action Title | Progress |
| --- | --- |
| Staff |  |

| Action Title | Progress |
| --- | --- |
| Skills and Knowledge |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SMT - broader awareness (eg board workshop attendance) and buddy system to ensure meeting/absence cover is not reliant on escalation | Lisa Hilder; Helen Kenyon |  | Ensuring SMT have broader knowledge and understanding of CCG working and priorities in order to cover in absence of Senior Managers; People to identify robust cross cover arrangements | Identify pairings | 31-May-2017 | Partially | To be reviewed in light of proposed closer working with the L.A. and potential changes in portfolios. More in-depth sharing of information has taken place as part of SMT time outs to begin to enable cross cover. |
|  |  |  |  |  | Enable broader cross cover | 30-Jun-2017 | Partially | As above |

| Action Title | Progress |
| --- | --- |
| Strategy |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Development of joint outcomes with Local Authority | Jan Haxby |  |  | Meet with Deputy CEO of NELC/CCG to scope the work | 31-May-2017 | Yes |  |
|  |  |  |  |  | Develop action plan to engage others | 19-Jun-2017 | No | Work is ongoing to achieve this |
|  |  |  |  |  | Take action plan and proposals to CoM and wider CCG/NELC consultation including Board | 31-Aug-2017 | No |  |
|  |  |  |  |  | Revise proposals and seek final agreements | 31-Oct-2017 | No |  |

| Action Title | Progress |
| --- | --- |
| Shared Values & Communications |  |

| Action Title | Progress |
| --- | --- |
| Urgent & Emergency Care |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Deliver improvement to rapid response at home to urgent care | Andy Ombler |  | Ensure delivery of the trajectory of reductions in emergency admissions | Establishing the programme | 30-Apr-2017 | No | .Actions have been taken to gain a better understanding of current responsiveness for the Rapid Response service and on the demand and response profile of the existing service. This has a target date of 1st September to complete. The intent to specify enhancements as i) Target responsiveness ( matching capacity to demand ), 2)A GP referrals service for home visits and 3)ambulance conveyance avoidance - have been stated with CPG. Milestone to be reviewed. |
|  |  |  |  |  | Assess potential for offer to primary care for a home visiting service | 31-Aug-2017 | No |  |
|  |  |  |  |  | Reducing affordable ambulance conveyance from home | 13-Nov-2017 | No |  |
|  |  |  |  |  | Matching demand and capacity in responsiveness of services | 31-Mar-2018 | No |  |

| Action Title | Progress |
| --- | --- |
| Women & Children's care |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Remodel Children’s community nursing from a consultant led, into a nurse led service | Michelle Thompson |  | Children and young people will have access to a community based nurse led service at a place and time which is appropriate to their needs Unnecessary hospital attendance and admission will be reduced | Set measurable KPI's | 30-Apr-2017 | No | There are currently issues in determining a new KPI data set. The data has been requested from NL&G in order to monitor and set targets but nothing has been forthcoming. The situation has been escalated. |
|  |  |  |  |  | Set up task and finish group | 31-May-2017 | Yes | completed |
|  |  |  |  |  | Review and refine service specification | 01-Dec-2017 | No |  |
|  |  |  |  |  | Re-modelled service operational | 31-Mar-2018 | No |  |

| Action Title | Progress |
| --- | --- |
| Planned Care: Episodic |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Review domiciliary care delivery model to transform service delivery from focus on time and task to team based delivery across local geographies focused on users’ wellbeing | Bev Compton |  | Increase user satisfaction with care delivery Improve health, well-being and independence of service users Increase opportunities for users to access community support and activities to reduce social isolation Increase service performance and efficiency | Pilot of the utopia street is being rolled out at Humberston; initial work is now being extended to additional area with the same provider | 30-Apr-2017 | Yes | Pilot is underway with few issues being raised |
|  |  |  |  |  | Evaluation of the model | 26-May-2017 | No | Initial evaluation work is being carried out |
|  |  |  |  |  | Full roll out | 30-Jun-2017 | No | Further consideration at Care Contracting Committee will be required |
|  | Referral to Treatment | Pauline Bamgbala |  | Ensure referral to treatment times meet the planned trajectories | Working with NL&G to ensure the data validation takes place | 31-May-2017 | Yes | 36,500 records have been validated and now moving to phase 2 where a further 20,000 records will be validated. In terms of meeting planned trajectory, this will not be achieved within the original timescale. Now looking at 2018. |
|  |  |  |  |  | Ensure NL&G undertake ongoing training of admin staff | 30-Jun-2017 | No | As part of the revalidation process, a training programme is in place for admin staff |

| Action Title | Progress |
| --- | --- |
| Planned Care: Longterm condition management |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Continue the roll out of the Long Term Conditions Enhanced Primary Care model for COPD, Cardiology, Diabetes and then across a range of other Long Term Conditions | Sarah Dawson |  | Reduce variation of care provided and outcomes within primary care for long term conditions | Develop diabetes pathway and clinical system templates | 19-Jun-2017 | No | Slipped due to planned sick leave Dr Bain – revised milestone date suggested 30 September |
|  |  |  |  |  | Complete COPD training with practice groups | 31-Jul-2017 | No | Progress has been made. New completion date end October 2017 |
|  |  |  |  |  | Complete training with practice groups | 31-Jan-2018 | No |  |
|  | Improve outcomes for vulnerable people that are eligible for health checks | Angie Dyson |  | Ensure primary care health checks are undertaken for those with learning disabilities and autism | Reviewing healthchecks for all vulnerable people across NEL and identify duplication with public health | 31-May-2017 | No | Work is still ongoing to complete this task |
|  |  |  |  |  | Ensure that people are aware that they are eligible for health checks | 31-Oct-2017 | No |  |
|  |  |  |  |  | Reviewing GP practices with regards LD health checks and ensure that we meet the required targets | 31-Dec-2017 | No |  |
|  | Extra Care Housing | Nicola McVeigh |  | Increase the choice of care models available within the NEL community so that people are encouraged to maintain their independence for as long as possible; Create a diversified range of tenures for extra care housing Reduce the cost of care Reduce unplanned hospital admissions Improve satisfaction with care provided Ensure that people within care settings feel safe and are safe | NELC cabinet agrees to a below market value disposal of Mathew Humberston site | 30-Apr-2017 | No | There is still no progress on the acquisition of the Mathew Humberstone site; the developer believes that the cost being charged for the site is over market valuation whereas the council believe that is it an appropriate valuation and responding to the developers offer would breach state aid rules; report for CCC will state that the CCG should pursue the Winchester avenue sites first whilst the negotiations are being concluded. |
|  |  |  |  |  | Site procurement for Ashley House | 31-Jul-2017 | No | Joint Venture meeting held on 8.5.17. Ashley House are tasked with remodelling the build cost financials to ensure they can deliver the rent levels required |
|  |  |  |  |  | Planning permission and site plans finalised | 29-Dec-2017 | No | Clarification required from Central Government on LHA issue and how top up is to be calculated. This remains an unknown risk at the moment (paper expected May/June 2017 but delay due to election likely). Briefing paper will be produced to go to CCC and Cabinet. Without a statement from Council/CCG as to their position regarding protecting the top up of rents (to include all proposed ECH sites) Ashley House and preferred housing provider Riverside will be unable to proceed with the development until decisions are reached. In the meantime developers will be encourage to provide mixed tenure options which would provide additional housing for general needs accommodation to mitigage the risks arising from the proposed welfare reform. |
|  |  |  |  |  | Commencement on site | 30-Mar-2018 | No | Progress will depend on resolution of LHA issues and Ashley House ability to reduce build cost to ensure acceptable rent levels. Crucially these issues need to be resolved for all ECH sites to proceed |

| Action Title | Progress |
| --- | --- |
| Primary Care |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Primary care workforce development: Reception Staff | Julie Wilson |  | Reduced GP workload Improved access to general practice services Improved retention of nursing staff | Complete training for coding of clinical paperwork | 30-Apr-2017 | Yes | Complete for administrative staff. GP training session was cancelled by the Provider. This has been re-scheduled for 26 May 2017 |
|  |  |  |  |  | Secure training provider for up-skilling of GP receptionist and admin staff | 30-May-2017 | No | Prover secured for correspondence management training and training completed. STP primary care leads area now seeking quotes navigation training. |
|  |  |  |  |  | Complete training for care navigation | 31-Oct-2017 | No |  |
|  | Primary care workforce development: Clinical Pharmacists | Julie Wilson |  | Reduced GP workload Improved access to general practice services | Submit bid for NHS England 2nd wave of clinical pharmacists | 30-Jun-2017 | No | NHSE now has minimum requirement for bids to cover 30,000 population and there are insufficient numbers across practices that have expressed interest thus far. Plan is to work with new practice groupings to identify additional interest to reach 30,000 population size |
|  |  |  |  |  | If bid successful, support practices to recruit and appoint clinical pharmacists | 30-Sep-2017 | No |  |

| Action Title | Progress |
| --- | --- |
| System Transformation |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Undertake a comprehensive review of adult services to ensure that current and future needs can be met within a significantly reduced financial envelope; | Bev Compton |  | Increase satisfaction with services for users and carers Improve service efficiency and effectiveness Manage demand Create effective and efficient preventative offer to reduce the need for statutory services and support | Action Plan developed | 31-May-2017 | No | This review is not being progressed due to other priorities within adult services and the need to use available capacity to support change initiatives. |
|  |  |  |  |  | Agreement of scope | 31-Jul-2017 | No | Completed |
|  |  |  |  |  | Procurement of a brief partner initiation of review | 31-Aug-2017 | No | Cancelled – remove from plan |
|  |  |  |  |  | Procurement of a brief partner Initiation of review | 30 Sep 2017 | No | Cancelled – remove rom plan |
|  |  |  |  |  | Brief created for review | 31-Oct-2017 | No | Cancelled – remove rom plan |
|  |  |  |  |  | Delivery of plan | 31-Mar-2018 | No | Cancelled – remove rom plan |
|  | Support move of CHC to the Haven and joint working with the Haven team | Bruce Bradshaw | 100% | Successful move and integration of CHC working to improve access to fast track | CHC team to move from Heritage House to St Andrews | 30-Jun-2017 | No | Move concluded |
|  | Ethical and Pragmatic Decision Making - refreshed policy | Bev Compton | 60% | All staff can confidently implement the refreshed policy and this is reflected in their work | Secure method for assessing implementation | 30-Apr-2017 | No | A series of actions have been agreed with Christine Jackson including embedding a discussion in the practice meetings with APs |
|  |  |  |  |  | Create plan to assess implementation | 31-May-2017 | No | Workshop held 30/06/2017 |
|  |  |  |  |  | Monitor implementation against plan | 31-Mar-2018 | No | Significant work has already been carried out to train key personnel and a report will be prepared for the CCC |

| Action Title | Progress |
| --- | --- |
| Team Objectives - Contracting |  |

| Action Title | Progress |
| --- | --- |
| Team Objectives - Finance |  |

| Action Title | Progress |
| --- | --- |
| Team Objectives - Performance |  |

| Action Title | Progress |
| --- | --- |
| Team Objectives - Quality |  |

| Status | Action Description | Assigned To | Progress Bar | Outcome | Milestone | Milestones Due Date | Milestones Completed | Milestone Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Further develop quality profiles for each organisation build on them further to include templates for performance, finance, etc | Jan Haxby |  | Create holistic profiles for each of our provider organisations held in one place | Complete the quality profiles | 31-May-2017 | No | Profiles agreed in draft format – to be finalised |
|  |  |  |  |  | Complete additional profile template as required | 30-Sep-2017 | No |  |
|  |  |  |  |  | Ensure robust processes for maintaining and updating profiles | 31-Dec-2017 | No |  |
|  |  |  |  |  | Scope the area of under performance of first analysis | 31-Aug-2017 | No |  |
|  |  |  |  |  | Establish the framework for each area of under performance | 30-Nov-2017 | No |  |
|  | Infection, prevention and control strategy for the CCG | Jan Haxby |  | Reduction in infection rates; Closer joint working with IPC professionals | Strategy in place | 31-May-2017 | No |  |
|  |  |  |  |  | Set up south bank IPC group | 30-Jun-2017 | No |  |
|  | Develop a clear serious incident strategy for social care providers and a system and process that manages it | Jan Haxby |  | A consistently implemented approach for dealing with Serious Incidents in social care | Agreeing the approach | 31-May-2017 | No | Draft strategy has been to quality committee – under review |
|  |  |  |  |  | Implementing the approach | 28-Feb-2018 | No |  |
|  |  |  |  |  | Training on the new approach | 28-Feb-2018 | No |  |
|  |  |  |  |  | Reviewing implementation | 31-Mar-2018 | No |  |

| Action Title | Progress |
| --- | --- |
| Team Objectives Communications & Engagement |  |

| Action Status Overdue; Neglected Check Progress Not Started; In Progress; Assigned Completed |  |  |
| --- | --- | --- |

# Text boxes

Agenda Item 06

Report to (Board/Sub-Committee):

Date of Meeting: 13th July 2017

Subject: Update on delivery of Corporate Business Plan

Presented by: Helen Kenyon

STATUS OF THE REPORT

For Information

For Discussion				x

For Approval / Ratification